## Forecast Calculator
Forecast Completion Date |  |  |  | Calculated Results
|  |  |  | Likelihood | Duration in Development Cycles | Delivery Development Cycle | End of Development Cycle
1. Start Date: | 2026-01-10 |  |  | 99% | 17 | 26.36 | 2026-09-05
Development Cycle |  |  |  | 95% | 16 | 26.34 | 2026-08-22
|  |  |  | 90% | 15 | 26.32 | 2026-08-08
2. How many work items are remaining to be completed? |  |  |  | 85% | 14 | 26.30 | 2026-07-25
|  |  |  | 80% | 14 | 26.30 | 2026-07-25
Low guess | 200 | High guess | 300 | 75% | 14 | 26.30 | 2026-07-25
|  |  |  | 70% | 13 | 26.28 | 2026-07-11
3. How often are work items split before and whilst being worked on? (Estimate the split rate of work items) |  |  |  | 65% | 13 | 26.28 | 2026-07-11
|  |  |  | 60% | 13 | 26.28 | 2026-07-11
Low guess | 1 | High guess | 1.5 | 55% | 12 | 26.26 | 2026-06-27
|  |  |  | 50% | 12 | 26.26 | 2026-06-27
|  |  |  | 45% | 12 | 26.26 | 2026-06-27
4. Input the throughput based on # of work items completed (development cycle = 2 Weeks) |  |  |  | 40% | 11 | 26.24 | 2026-06-13
|  |  |  | 35% | 11 | 26.24 | 2026-06-13
Low Throughput | 30 | High Throughput | 60 | 30% | 11 | 26.24 | 2026-06-13
|  |  |  | 25% | 11 | 26.24 | 2026-06-13
5. What is the capacity of Teams at any time? (in %) |  |  |  | 20% | 10 | 26.22 | 2026-05-30
|  |  |  | 15% | 10 | 26.22 | 2026-05-30
Low capacity | 40 | High capacity | 80 | 10% | 10 | 26.22 | 2026-05-30
|  |  |  | 5% | 9 | 26.20 | 2026-05-16
|  |  |  | 0% | 7 | 26.16 | 2026-04-18
https://therevolutionarymind.at
Formulas:
Delivery Development Cycle = RIGHT(Year([End of Development Cycle]),2)&"."&IF(LEN(WEEKNUM([End of Development Cycle],21))<2,"0"&WEEKNUM([End of Development Cycle],21),WEEKNUM([End of Development Cycle],21))
End of Development Cycle = PERCENTILE(Probabilistic_Data_Simulation!$C3:C600,[Likelihood])

## Tracking
Tracking / Control Data
Start Date | End Date | Development Cycle | Total Scope Forecast (80%) | Delivered Forecast (80%) | Real Scope | Real Delivered (Cumulative) | Work Items Delivered | Work Items Added / Removed | Actual Capacity Invested | Important Notes
2026-01-10 | 2026-01-24 | 26.04 | 333.118 | 24.882 | 78 | 7 | 7 | -255.118
2026-01-24 | 2026-02-07 | 26.06 | 333.118 | 52.818 | 90 | 10 | 3 | 12
2026-02-07 | 2026-02-21 | 26.08 | 333.118 | 79.664 | 100 | 15 | 5 | 10
2026-02-21 | 2026-03-07 | 26.10 | 333.118 | 106.456 | 100 | 22 | 7 | 0
2026-03-07 | 2026-03-21 | 26.12 | 333.118 | 128.6584 | 100 | 30 | 8 | 0
2026-03-21 | 2026-04-04 | 26.14 | 333.118 | 155.2564 | 100 | 36 | 6 | 0
2026-04-04 | 2026-04-18 | 26.16 | 333.118 | 182.9264 | 100 | 40 | 4 | 0
2026-04-18 | 2026-05-02 | 26.18 | 333.118 | 209.9164 | 100 | 45 | 5 | 0
2026-05-02 | 2026-05-16 | 26.20 | 333.118 | 236.6284 | 100 | 60 | 15 | 0
2026-05-16 | 2026-05-30 | 26.22 | 333.118 | 267.8916 | 100 | 65 | 5 | 0
2026-05-30 | 2026-06-13 | 26.24 | 333.118 | 291.7764 | 100 | 85 | 20 | 0
2026-06-13 | 2026-06-27 | 26.26 | 333.118 | 320.7756 | 100 | 100 | 15 | 0
2026-06-27 | 2026-07-11 | 26.28 | 333.118 | 344.6274 | 100 | 100 | 0 | 0
2026-07-11 | 2026-07-25 | 26.30 | 333.118 | 354.6814 | 100 | 100 | 0 | 0
2026-07-25 | 2026-08-08 | 26.32 | 333.118 | 354.6814 | 100 | 100 | 0 | 0
2026-08-08 | 2026-08-22 | 26.34 | 333.118 | 354.6814 | 110 | 110 | 10 | 10
Tracking / Control Chart
Formulas:
Development Cycle = RIGHT(Year([Start Date]),2)&"."&IF(LEN(WEEKNUM([Start Date],21)+2)<2,"0"&WEEKNUM([Start Date],21)+2,WEEKNUM([Start Date],21)+2)

## Probabilistic_Data_Simulation
Trial | Weeks to Zero | End of Zero Week | TotalStories | End period 1 | End period 2 | End period 3 | End period 4 | End period 5 | End period 6 | End period 7 | End period 8 | End period 9 | End period 10 | End period 11 | End period 12 | End period 13 | End period 14 | End period 15 | End period 16 | End period 17 | End period 18 | End period 19 | End period 20 | End period 21 | End period 22 | End period 23 | End period 24 | End period 25 | End period 26 | End period 27 | End period 28 | End period 29 | End period 30 | End period 31 | End period 32 | End period 33 | End period 34 | End period 35 | End period 36 | End period 37 | End period 38 | End period 39 | End period 40 | End period 41 | End period 42 | End period 43 | End period 44 | End period 45 | End period 46 | End period 47 | End period 48 | End period 49 | End period 50 | End period 51 | End period 52
 | time axis 2026-01-10 to 2028-01-08
1 | 9 | 2026-05-16 | 273 | 242.66 | 214.14 | 192.14 | 153.38 | 113.42 | 88.85 | 56.35 | 26.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 13 | 2026-07-11 | 330 | 305.51 | 278.48 | 238.58 | 214.58 | 187.9 | 154.96 | 133.34 | 110.94 | 89.32 | 65.89 | 36.77 | 9.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 14 | 2026-07-25 | 318 | 300.45 | 271.83 | 235.87 | 211.69 | 192.42 | 172.21 | 149.01 | 131.61 | 105.37 | 82.93 | 65.73 | 43.97 | 13.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 11 | 2026-06-13 | 274 | 249.22 | 215.83 | 192.51 | 167.57 | 137.96 | 105.57 | 77.84 | 46.27 | 24.22 | 5.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 11 | 2026-06-13 | 338 | 305.6 | 265.13 | 231.33 | 187.88 | 164.85 | 136.05 | 95.24 | 74.24 | 35.99 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 12 | 2026-06-27 | 286 | 263.45 | 230.45 | 207.51 | 191.06 | 170.41 | 142.29 | 107.79 | 93.27 | 70.17 | 43.53 | 11.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 11 | 2026-06-13 | 296 | 269.9 | 243.4 | 211.16 | 185.78 | 165.62 | 148.4 | 122.13 | 95.13 | 51.93 | 9.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 11 | 2026-06-13 | 301 | 274 | 227.39 | 186.58 | 148.08 | 127.99 | 107.49 | 83.19 | 60.93 | 29.01 | 9.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | 16 | 2026-08-22 | 395 | 362.66 | 337.7 | 317 | 288.4 | 266.95 | 234.12 | 218.52 | 198.24 | 158.71 | 123.94 | 97.9 | 75.81 | 57.11 | 33.91 | 4.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 13 | 2026-07-11 | 310 | 271.12 | 244.62 | 217.67 | 199.82 | 183.02 | 159.52 | 124.75 | 105.67 | 85.95 | 61.95 | 26.07 | 1.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | 11 | 2026-06-13 | 303 | 277.8 | 240.6 | 210.24 | 164.64 | 150.84 | 113.74 | 86.48 | 64.38 | 40.37 | 2.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | 11 | 2026-06-13 | 278 | 257.42 | 230.54 | 201.56 | 183.01 | 142.89 | 108.11 | 85.43 | 64.73 | 39.53 | 15.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 11 | 2026-06-13 | 273 | 247.92 | 207.04 | 191.92 | 179.62 | 152.36 | 122.6 | 93.6 | 64.8 | 45.06 | 8.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 11 | 2026-06-13 | 309 | 280.33 | 248.65 | 231.69 | 202.54 | 167.14 | 129.14 | 102.89 | 66.63 | 42.33 | 18.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | 10 | 2026-05-30 | 295 | 267.7 | 239.2 | 195.12 | 158.93 | 123.89 | 99.25 | 61.06 | 21.46 | 0.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | 10 | 2026-05-30 | 258 | 230.64 | 209.02 | 193.51 | 168.14 | 139.23 | 106.99 | 66.11 | 49.94 | 10.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | 9 | 2026-05-16 | 262 | 229.15 | 189.73 | 166.21 | 130.81 | 89.77 | 61.33 | 32.1 | 10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | 10 | 2026-05-30 | 283 | 266.28 | 243.32 | 206.84 | 179.93 | 140.6 | 123.58 | 82.77 | 62.29 | 33.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 13 | 2026-07-11 | 325 | 296.5 | 253.58 | 230.36 | 202.76 | 172.66 | 134.26 | 118.66 | 96.52 | 73.42 | 53.07 | 22.67 | 0.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 | 12 | 2026-06-27 | 341 | 306 | 287.09 | 255.17 | 216.17 | 191.09 | 164.25 | 136.51 | 108.95 | 78.13 | 35.21 | 5.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 10 | 2026-05-30 | 255 | 241.8 | 220.3 | 196.6 | 158.44 | 135.64 | 94.46 | 58.06 | 33.31 | 11.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
22 | 12 | 2026-06-27 | 281 | 252.86 | 227.56 | 204.2 | 182.2 | 155.06 | 132.56 | 107.08 | 86.17 | 68.11 | 33.34 | 11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 9 | 2026-05-16 | 241 | 206.44 | 192.8 | 174.76 | 148.36 | 114.14 | 82.9 | 51.22 | 24.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 12 | 2026-06-27 | 316 | 286.52 | 253.52 | 235.48 | 208.53 | 173.76 | 146.24 | 112.4 | 80.91 | 63.71 | 46.94 | 22.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
25 | 7 | 2026-04-18 | 234 | 192.11 | 169.69 | 137.26 | 103.45 | 63.85 | 22.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
26 | 14 | 2026-07-25 | 377 | 354.5 | 333.04 | 308.85 | 268.57 | 244.72 | 216.12 | 187.65 | 146.31 | 102.86 | 80.36 | 45.6 | 28.79 | 7.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 | 14 | 2026-07-25 | 363 | 343.76 | 323.36 | 299.51 | 278.01 | 253.81 | 232.25 | 196.26 | 161.28 | 146.52 | 103.92 | 74.85 | 55.13 | 18.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | 12 | 2026-06-27 | 304 | 287.19 | 264.75 | 242.25 | 225.45 | 210.88 | 188.84 | 159.69 | 118.39 | 93.64 | 66.6 | 28.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 11 | 2026-06-13 | 267 | 242.16 | 217.52 | 193.52 | 167.87 | 129.68 | 111.53 | 87.85 | 58.85 | 33.84 | 11.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 | 9 | 2026-05-16 | 254 | 210.68 | 188.26 | 164.48 | 138.24 | 119.16 | 76.82 | 39.86 | 0.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
31 | 13 | 2026-07-11 | 360 | 327.24 | 303.68 | 279.83 | 241.35 | 214.35 | 191.25 | 160.7 | 132.14 | 88.34 | 65.94 | 39.54 | 11.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 9 | 2026-05-16 | 234 | 196.6 | 170.2 | 144.74 | 109.24 | 89.44 | 64.5 | 34.08 | 8.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 13 | 2026-07-11 | 313 | 283.5 | 244.56 | 212.94 | 198.09 | 176.33 | 158.7 | 137.7 | 113.61 | 89.19 | 65.69 | 38.89 | 7.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
34 | 13 | 2026-07-11 | 352 | 330.93 | 311.73 | 281.39 | 252.51 | 232.42 | 187.96 | 162.04 | 144.22 | 126.62 | 95.88 | 69.48 | 28.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
35 | 11 | 2026-06-13 | 263 | 243.65 | 208.31 | 180.79 | 140.64 | 101.7 | 83.3 | 66.2 | 46.4 | 31.68 | 6.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
36 | 12 | 2026-06-27 | 358 | 340.5 | 294.1 | 264.9 | 221.01 | 198.06 | 178.46 | 130.46 | 105 | 81 | 49.84 | 17.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 11 | 2026-06-13 | 299 | 273.52 | 248.92 | 226.38 | 208.75 | 182.07 | 146.73 | 111.45 | 83.37 | 45.45 | 28.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
38 | 14 | 2026-07-25 | 342 | 324.14 | 295.64 | 273.68 | 251.6 | 224.04 | 180.97 | 140.69 | 117.91 | 100.76 | 66.56 | 45.36 | 25.86 | 0.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
39 | 13 | 2026-07-11 | 354 | 316.4 | 283.1 | 249.35 | 225.35 | 200.39 | 164.2 | 141.45 | 121.95 | 81.35 | 46.58 | 27.23 | 11.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 | 13 | 2026-07-11 | 336 | 317.6 | 297.35 | 266.55 | 240 | 221.94 | 194.96 | 158.56 | 127.06 | 106.41 | 78.91 | 41.47 | 16.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
41 | 12 | 2026-06-27 | 284 | 247.46 | 213.86 | 195.62 | 170.83 | 149.23 | 105.73 | 91.73 | 69.17 | 40.79 | 22.73 | 7.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
42 | 10 | 2026-05-30 | 253 | 222.2 | 193.13 | 157.71 | 139.85 | 127.05 | 94.6 | 68.8 | 41.5 | 19.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
43 | 12 | 2026-06-27 | 287 | 263.22 | 235.16 | 194.56 | 173.14 | 153.3 | 129.74 | 93.86 | 72.71 | 42.55 | 23.44 | 9.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 12 | 2026-06-27 | 298 | 276.65 | 231.05 | 211.05 | 193.45 | 178.88 | 138.32 | 119.84 | 89.95 | 72.09 | 44.19 | 12.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45 | 8 | 2026-05-02 | 206 | 178.53 | 136.66 | 113.3 | 76.9 | 57.54 | 21.35 | 4.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
46 | 10 | 2026-05-30 | 293 | 266.68 | 228.95 | 211.59 | 181.66 | 144.61 | 103.01 | 70.01 | 44.36 | 25.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
47 | 15 | 2026-08-08 | 359 | 339.2 | 292.8 | 271.38 | 252.58 | 237.07 | 207.57 | 177.17 | 161.87 | 136.71 | 120.61 | 102.37 | 81.47 | 36.23 | 10.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
48 | 11 | 2026-06-13 | 294 | 271.86 | 243.74 | 217.34 | 181.92 | 136.32 | 106.11 | 79.93 | 60.33 | 32.64 | 11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
49 | 8 | 2026-05-02 | 211 | 176.78 | 148.83 | 119.22 | 82.12 | 65.12 | 39.71 | 14.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 | 10 | 2026-05-30 | 238 | 218.8 | 197.64 | 176.56 | 157.04 | 132.86 | 103.61 | 73.37 | 51.53 | 11.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
51 | 12 | 2026-06-27 | 307 | 275.05 | 243.07 | 221.92 | 207.3 | 177.66 | 155.73 | 129.51 | 85.62 | 60.66 | 26.35 | 7.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
52 | 14 | 2026-07-25 | 371 | 345 | 313.95 | 271.77 | 234.04 | 217.32 | 193.32 | 158.36 | 121.64 | 98.64 | 76.2 | 51.42 | 28.92 | 8.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
53 | 13 | 2026-07-11 | 336 | 321.28 | 282.01 | 253.31 | 218.5 | 196.06 | 156.54 | 121.26 | 97.34 | 65.34 | 42.94 | 21.16 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
54 | 11 | 2026-06-13 | 274 | 233.98 | 205 | 171.52 | 152.48 | 135.32 | 110.88 | 95.7 | 65.34 | 37.29 | 3.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
55 | 11 | 2026-06-13 | 279 | 263.7 | 230.76 | 207.31 | 180.85 | 149.49 | 127.89 | 101.01 | 65.01 | 33.05 | 17.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
56 | 15 | 2026-08-08 | 356 | 328.26 | 287.66 | 267.42 | 247.74 | 228.47 | 204.71 | 179.55 | 157.11 | 137.73 | 102.54 | 83.19 | 51.92 | 28.74 | 4.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
57 | 12 | 2026-06-27 | 352 | 323.2 | 283.3 | 243.86 | 196.46 | 178.4 | 154 | 118.3 | 98.52 | 68.88 | 39.2 | 6.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
58 | 16 | 2026-08-22 | 386 | 360.15 | 325.95 | 298 | 263.6 | 239.16 | 215.84 | 190.83 | 174.38 | 156.46 | 138.17 | 101.45 | 79.4 | 61.85 | 36.65 | 11.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
59 | 10 | 2026-05-30 | 283 | 243.47 | 222.79 | 183.04 | 152.95 | 121.45 | 97.69 | 78.79 | 46.4 | 24.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 | 14 | 2026-07-25 | 365 | 347.45 | 319.5 | 289.14 | 270.81 | 244.15 | 203.86 | 174.28 | 155.08 | 131.14 | 90.34 | 43.73 | 21.29 | 0.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
61 | 12 | 2026-06-27 | 321 | 302.94 | 277.52 | 245.09 | 226.19 | 190.28 | 168.93 | 149.13 | 129.86 | 96.49 | 58.75 | 23.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
62 | 13 | 2026-07-11 | 337 | 303.4 | 276.04 | 246.88 | 224.62 | 186.82 | 162.18 | 145.02 | 123.82 | 93.66 | 75.26 | 60.38 | 36.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
63 | 9 | 2026-05-16 | 269 | 240.2 | 204.5 | 161.3 | 138.51 | 111.21 | 83.61 | 43.33 | 11.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
64 | 11 | 2026-06-13 | 284 | 267.68 | 243.04 | 204.28 | 185.08 | 162.68 | 140.57 | 109.82 | 79.66 | 56.1 | 21.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
65 | 12 | 2026-06-27 | 319 | 293.84 | 269.99 | 242.49 | 210.49 | 178.06 | 133.06 | 106.42 | 81.22 | 57.82 | 27.9 | 5.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
66 | 14 | 2026-07-25 | 337 | 318.52 | 294.16 | 271.06 | 248.74 | 232.57 | 207.37 | 180.01 | 153.06 | 105.66 | 67.02 | 47.24 | 21.2 | 1.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
67 | 11 | 2026-06-13 | 322 | 275.2 | 242.37 | 219.01 | 195.21 | 159.33 | 131.21 | 107.96 | 68.54 | 45.32 | 8.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
68 | 13 | 2026-07-11 | 321 | 288.44 | 269.44 | 241.51 | 219.91 | 194.95 | 163.27 | 134.15 | 104.23 | 87.51 | 61.38 | 39.76 | 1.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
69 | 10 | 2026-05-30 | 281 | 263.6 | 220.4 | 182.24 | 146.88 | 106.68 | 82.71 | 65.31 | 35.55 | 21.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 | 10 | 2026-05-30 | 246 | 229.36 | 208.01 | 178.01 | 149.69 | 120.54 | 104.9 | 70.14 | 49.07 | 19.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
71 | 12 | 2026-06-27 | 345 | 318.48 | 280.14 | 253.68 | 220.92 | 190.52 | 163.22 | 134.31 | 94.31 | 68.34 | 38.58 | 5.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
72 | 13 | 2026-07-11 | 290 | 268.88 | 253.52 | 225.64 | 201.64 | 181 | 144.2 | 123.2 | 106.04 | 88.28 | 68.56 | 38.2 | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
73 | 17 | 2026-09-05 | 430 | 403.48 | 381.92 | 360.47 | 332.63 | 315.41 | 275.63 | 255.11 | 232.97 | 197.46 | 175.06 | 143.16 | 118.15 | 78.19 | 47.59 | 23.21 | 7.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
74 | 11 | 2026-06-13 | 262 | 246.32 | 220.1 | 195.61 | 179.61 | 163.11 | 123.78 | 107.58 | 84.9 | 49.35 | 17.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
75 | 12 | 2026-06-27 | 305 | 280.8 | 253.8 | 212.76 | 192.67 | 175.62 | 131.16 | 109.54 | 89.54 | 54.02 | 30.08 | 8.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
76 | 8 | 2026-05-02 | 243 | 220.64 | 178.52 | 140.02 | 98.68 | 74.08 | 56.72 | 25.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
77 | 14 | 2026-07-25 | 375 | 353 | 323.6 | 298.85 | 259.85 | 238.94 | 215.57 | 188.21 | 156.97 | 135.9 | 116.29 | 79.57 | 62.08 | 32.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
78 | 14 | 2026-07-25 | 349 | 323.63 | 299.25 | 273.6 | 248.78 | 234.5 | 208 | 165.44 | 133.46 | 111.8 | 85.84 | 65.04 | 42.49 | 16.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
79 | 11 | 2026-06-13 | 293 | 266.21 | 226.99 | 206.31 | 163.19 | 148.49 | 117.75 | 80.25 | 59.55 | 42.19 | 18.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 | 13 | 2026-07-11 | 339 | 320.85 | 290.49 | 264.89 | 233.04 | 201.68 | 159.68 | 128.48 | 103.64 | 70.64 | 50.9 | 30.84 | 11.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
81 | 15 | 2026-08-08 | 377 | 356.87 | 335.27 | 293.87 | 278.29 | 246.05 | 229.88 | 217.17 | 193.09 | 160.75 | 140.66 | 116.98 | 73.78 | 52.54 | 19.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
82 | 13 | 2026-07-11 | 373 | 345.48 | 317.75 | 294.63 | 259.91 | 221.99 | 198.39 | 175.08 | 145.16 | 123.38 | 89.08 | 53.72 | 34.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
83 | 12 | 2026-06-27 | 298 | 270.8 | 245.86 | 228.26 | 204.07 | 183.39 | 161.07 | 117.27 | 93.75 | 62.55 | 45.27 | 5.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
84 | 13 | 2026-07-11 | 312 | 282.6 | 259.56 | 237.47 | 214.67 | 195.06 | 174.15 | 146.22 | 125.87 | 93.97 | 72.77 | 45.91 | 21.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
85 | 16 | 2026-08-22 | 383 | 356 | 338.52 | 308.12 | 290.14 | 254.59 | 229.22 | 209.12 | 183.02 | 148.46 | 135.13 | 108.61 | 83.15 | 54.29 | 37.27 | 3.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
86 | 14 | 2026-07-25 | 335 | 311.57 | 294.41 | 266.35 | 245.85 | 213.37 | 182.1 | 153.48 | 133.68 | 109.32 | 91.02 | 62.42 | 40.16 | 8.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
87 | 9 | 2026-05-16 | 270 | 229.72 | 199.9 | 157.15 | 136.35 | 106.01 | 84.93 | 65.61 | 24.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
88 | 13 | 2026-07-11 | 339 | 316.86 | 296.7 | 269.2 | 246.41 | 221.71 | 190.51 | 153.41 | 138.65 | 114.29 | 81.11 | 40.23 | 16.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
89 | 10 | 2026-05-30 | 266 | 234.15 | 213.65 | 183.73 | 147.01 | 116.76 | 89.48 | 63.72 | 48.08 | 17.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 | 12 | 2026-06-27 | 302 | 279.22 | 258.98 | 240.62 | 216.54 | 199.38 | 173.41 | 142.61 | 121.49 | 77.25 | 46.43 | 14.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
91 | 13 | 2026-07-11 | 343 | 309.88 | 278.38 | 239.98 | 207.22 | 184.42 | 163.36 | 141.16 | 120.16 | 100.03 | 61.32 | 38.9 | 6.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
92 | 10 | 2026-05-30 | 280 | 259.09 | 232.81 | 198.51 | 173.73 | 139.92 | 115.28 | 91.28 | 64.28 | 25.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
93 | 13 | 2026-07-11 | 343 | 318.15 | 287.41 | 265.97 | 238.13 | 196.83 | 167.67 | 147.27 | 110.07 | 84.87 | 59.35 | 30.73 | 3.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
94 | 9 | 2026-05-16 | 253 | 236.68 | 210.68 | 177.56 | 158.96 | 133.52 | 106.07 | 76.4 | 32.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
95 | 10 | 2026-05-30 | 226 | 203.8 | 174.8 | 138.81 | 120.99 | 96.03 | 64.05 | 46.89 | 25.33 | 1.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
96 | 13 | 2026-07-11 | 335 | 296.6 | 264.7 | 234.1 | 211.47 | 169.35 | 145.59 | 123.51 | 88.72 | 63.17 | 39.65 | 24.47 | 1.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
97 | 15 | 2026-08-08 | 346 | 311 | 290.79 | 272.73 | 243.53 | 225.71 | 200.06 | 181.61 | 150.59 | 134.27 | 104.57 | 80.77 | 57.67 | 38.67 | 12.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
98 | 13 | 2026-07-11 | 321 | 302.4 | 275.34 | 254.99 | 231.96 | 203.96 | 181.01 | 157.16 | 136.76 | 113.54 | 80.64 | 51.39 | 8.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | 11 | 2026-06-13 | 300 | 269.64 | 228.06 | 202.06 | 175.06 | 159.46 | 139.74 | 100.54 | 85.84 | 47.08 | 25.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 | 11 | 2026-06-13 | 295 | 259.12 | 232.47 | 204.31 | 167.51 | 145.46 | 122.66 | 102.16 | 73.05 | 53.85 | 19.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 12 | 2026-06-27 | 269 | 245.96 | 223.52 | 198.58 | 180.73 | 164.98 | 131.5 | 115.51 | 95.11 | 75.91 | 51.27 | 22.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
102 | 15 | 2026-08-08 | 382 | 337.54 | 303.32 | 277.86 | 264.26 | 242.16 | 202.89 | 181.47 | 167.97 | 134.93 | 120.58 | 105.62 | 84.92 | 49.2 | 34.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
103 | 11 | 2026-06-13 | 306 | 286.64 | 258.15 | 238.55 | 203.03 | 167.53 | 133.21 | 86.81 | 55.21 | 33.11 | 4.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
104 | 15 | 2026-08-08 | 387 | 366.6 | 330.1 | 309.19 | 281.69 | 260.6 | 224.6 | 201.28 | 176.8 | 155.07 | 116.88 | 92.44 | 65.24 | 36.82 | 17.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
105 | 14 | 2026-07-25 | 340 | 320.68 | 303.05 | 281.29 | 255.01 | 229.51 | 200.03 | 165.19 | 142.93 | 128.08 | 112.44 | 88.76 | 45.86 | 11.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
106 | 13 | 2026-07-11 | 350 | 331.08 | 297.48 | 268.98 | 234.48 | 216.46 | 183.34 | 157.6 | 133.95 | 102.79 | 79.34 | 55.15 | 15.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
107 | 11 | 2026-06-13 | 328 | 287.4 | 249.78 | 206.46 | 182.7 | 165.48 | 140.28 | 101.88 | 62.83 | 43.79 | 21.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
108 | 10 | 2026-05-30 | 286 | 258 | 238 | 205.5 | 170.85 | 136.2 | 110.78 | 85.36 | 45.86 | 9.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
109 | 10 | 2026-05-30 | 272 | 225.39 | 200.01 | 179.33 | 154.58 | 130.71 | 86.91 | 58.11 | 24.36 | 0.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
110 | 15 | 2026-08-08 | 328 | 309.14 | 283.31 | 268.61 | 251.27 | 224.59 | 200.08 | 165.32 | 145.72 | 118.68 | 96.72 | 82.77 | 58.2 | 29.06 | 3.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
111 | 17 | 2026-09-05 | 424 | 390.63 | 364.17 | 330.87 | 312.37 | 282.89 | 257.41 | 239.26 | 224.14 | 190.04 | 167.54 | 142.34 | 125.68 | 102.56 | 68.26 | 44.26 | 11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
112 | 13 | 2026-07-11 | 300 | 273.45 | 237.68 | 215.92 | 192.16 | 175.5 | 153.24 | 138.89 | 115.93 | 82.05 | 62.05 | 41.35 | 19.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
113 | 11 | 2026-06-13 | 275 | 244.22 | 209.12 | 183.02 | 162.14 | 139.64 | 117.81 | 81.15 | 53.1 | 28.32 | 0.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
114 | 11 | 2026-06-13 | 312 | 270.96 | 249.51 | 224.73 | 185.51 | 160.52 | 124.33 | 92.09 | 61.85 | 47.77 | 10.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
115 | 16 | 2026-08-22 | 358 | 331 | 314.55 | 288.45 | 266.01 | 249.73 | 233.56 | 215.43 | 182.67 | 152.99 | 131.67 | 106.02 | 82.32 | 61.41 | 44.61 | 16.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
116 | 13 | 2026-07-11 | 339 | 311.96 | 283.54 | 261.14 | 222.14 | 190.94 | 166.62 | 142.2 | 116.07 | 91.95 | 67.95 | 24.27 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
117 | 10 | 2026-05-30 | 282 | 262.8 | 239.85 | 205.69 | 178.83 | 141.63 | 100.05 | 75.67 | 46.79 | 11.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
118 | 10 | 2026-05-30 | 238 | 217.3 | 189.16 | 174.36 | 147.9 | 115.92 | 94.57 | 75.77 | 51.57 | 24.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
119 | 13 | 2026-07-11 | 397 | 377.48 | 344.48 | 310.88 | 271.12 | 241.52 | 215.6 | 171.94 | 141.16 | 115.75 | 95.29 | 59.1 | 23.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
120 | 10 | 2026-05-30 | 215 | 190.5 | 170.4 | 151.52 | 131.74 | 111.53 | 90.83 | 65.92 | 20.68 | 4.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
121 | 10 | 2026-05-30 | 303 | 271.32 | 244.06 | 208.86 | 173.76 | 135 | 102.84 | 86.03 | 57.71 | 28.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
122 | 13 | 2026-07-11 | 329 | 309.8 | 276.62 | 254.53 | 229.33 | 207.32 | 182.9 | 152.98 | 128.02 | 97.86 | 80.71 | 56.21 | 11.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
123 | 11 | 2026-06-13 | 287 | 259.86 | 228.54 | 211.77 | 196.26 | 173.54 | 149.84 | 106.92 | 83.12 | 55.03 | 14.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
124 | 13 | 2026-07-11 | 309 | 290.71 | 262.51 | 239.63 | 200.75 | 186.05 | 146.53 | 118.06 | 90.22 | 68.62 | 56.32 | 35.6 | 10.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
125 | 14 | 2026-07-25 | 336 | 302.68 | 274.24 | 249.6 | 229.02 | 207.42 | 188.62 | 168.52 | 140.52 | 118.16 | 96.26 | 63.7 | 39.7 | 4.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
126 | 16 | 2026-08-22 | 407 | 380.75 | 358.03 | 338.76 | 307.26 | 282.06 | 260.91 | 228.05 | 190.55 | 172.57 | 142.17 | 115.57 | 98.29 | 61.57 | 31.81 | 2.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
127 | 13 | 2026-07-11 | 335 | 300.44 | 279.77 | 265.07 | 225.29 | 199.55 | 172.11 | 143.97 | 121.96 | 83.56 | 53.18 | 32.18 | 8.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
128 | 14 | 2026-07-25 | 337 | 315.93 | 301.23 | 284.49 | 242.01 | 222.01 | 195.91 | 180.41 | 159.73 | 116.41 | 93.97 | 69.97 | 51.52 | 17.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
129 | 9 | 2026-05-16 | 247 | 225.84 | 191.19 | 168.63 | 137.43 | 113.78 | 81.78 | 47.74 | 20.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
130 | 13 | 2026-07-11 | 340 | 314.8 | 271.6 | 250.9 | 225.3 | 211.77 | 195.87 | 169.27 | 127.83 | 100.85 | 77.89 | 37.39 | 17.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
131 | 12 | 2026-06-27 | 293 | 269.88 | 250.27 | 231.91 | 195.19 | 157.59 | 143.73 | 96.93 | 77.49 | 54.55 | 30.55 | 9.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
132 | 13 | 2026-07-11 | 374 | 348.8 | 328.4 | 302.6 | 273.6 | 242.33 | 217.03 | 179.03 | 154.65 | 125.01 | 83.12 | 57.77 | 32.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
133 | 12 | 2026-06-27 | 363 | 331.8 | 289.8 | 248.92 | 202.31 | 172.91 | 127.67 | 107.15 | 82.97 | 62.76 | 45.12 | 18.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
134 | 14 | 2026-07-25 | 351 | 314.5 | 287.66 | 264.7 | 230.4 | 215.4 | 198.3 | 177.3 | 162.54 | 141.75 | 118.53 | 91.58 | 56.8 | 19.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
135 | 10 | 2026-05-30 | 293 | 251.6 | 211 | 176.02 | 153.23 | 123.83 | 94.97 | 65.97 | 24.93 | 3.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
136 | 13 | 2026-07-11 | 284 | 260.6 | 240.5 | 218.6 | 186.68 | 170.04 | 141.62 | 112.76 | 100.76 | 81.62 | 48.04 | 22.08 | 0.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
137 | 11 | 2026-06-13 | 312 | 274.24 | 233.16 | 205.47 | 183.15 | 160.89 | 140.21 | 104.21 | 73.43 | 51.38 | 17.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
138 | 15 | 2026-08-08 | 364 | 339.36 | 314.01 | 291.92 | 261.56 | 233.06 | 214.02 | 195.78 | 156.78 | 139.58 | 115.1 | 80.9 | 62.84 | 37.88 | 6.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
139 | 13 | 2026-07-11 | 348 | 311.74 | 296.44 | 270.04 | 229.24 | 209.86 | 173.98 | 140.68 | 110.92 | 80.17 | 57.38 | 42.19 | 8.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
140 | 14 | 2026-07-25 | 380 | 335.76 | 316.16 | 292.08 | 267.09 | 250.07 | 226.1 | 200.62 | 170.62 | 127.3 | 92.05 | 69.65 | 47.56 | 11.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
141 | 15 | 2026-08-08 | 371 | 348.95 | 315.45 | 293.85 | 273.69 | 252.61 | 214.33 | 200.53 | 184.85 | 165.25 | 136.11 | 107.07 | 68.31 | 45.51 | 18.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
142 | 12 | 2026-06-27 | 288 | 257 | 239.15 | 198.44 | 180.77 | 152.17 | 131.02 | 110.11 | 82.27 | 57.79 | 35.75 | 7.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
143 | 10 | 2026-05-30 | 276 | 249.48 | 209.88 | 182.38 | 162.58 | 132.88 | 92.84 | 72.16 | 39.12 | 12.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
144 | 8 | 2026-05-02 | 220 | 180.4 | 165.55 | 131.45 | 106.7 | 68.9 | 32.42 | 12.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
145 | 12 | 2026-06-27 | 285 | 256.86 | 231.78 | 205.38 | 191.88 | 168.42 | 154.47 | 128.97 | 105.6 | 75.45 | 61.05 | 18.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
146 | 13 | 2026-07-11 | 366 | 342.44 | 307.4 | 280.94 | 250.12 | 222.62 | 190.14 | 164.38 | 118.36 | 91.86 | 60.5 | 25.69 | 7.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
147 | 13 | 2026-07-11 | 357 | 334.32 | 295.98 | 259.77 | 221.01 | 196.82 | 165.14 | 146.64 | 128.16 | 103.22 | 74.36 | 43 | 17.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
148 | 16 | 2026-08-22 | 388 | 372.16 | 341.92 | 321.68 | 303.12 | 266.72 | 246.83 | 227.97 | 193.75 | 163.35 | 137.85 | 124.73 | 100.09 | 60.09 | 39.09 | 15.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
149 | 12 | 2026-06-27 | 282 | 267.2 | 241.28 | 213.28 | 185.74 | 162.86 | 137.26 | 105.99 | 68.19 | 47.55 | 23.76 | 10.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
150 | 16 | 2026-08-22 | 358 | 339.4 | 314.76 | 274.86 | 252.3 | 231.5 | 216 | 188.16 | 162.7 | 150.1 | 124.66 | 103.24 | 84.32 | 57.37 | 35.29 | 14.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
151 | 13 | 2026-07-11 | 309 | 279.88 | 249.85 | 227.65 | 195.25 | 170.77 | 147.67 | 117.91 | 100.95 | 83.03 | 42.32 | 18.53 | 0.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
152 | 10 | 2026-05-30 | 259 | 236.91 | 197.47 | 162.69 | 125.57 | 104.27 | 85.39 | 69.48 | 40.33 | 21.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
153 | 9 | 2026-05-16 | 220 | 194.35 | 182.35 | 145.09 | 106.33 | 86.95 | 65.89 | 39.99 | 13.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
154 | 18 | 2026-09-19 | 429 | 397.68 | 379.68 | 365.88 | 344.81 | 316.97 | 289.97 | 272.15 | 252.88 | 228.56 | 204.8 | 169.99 | 131.35 | 95.97 | 79.59 | 61.19 | 43.91 | 21.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
155 | 16 | 2026-08-22 | 389 | 367.4 | 336.16 | 307.74 | 284.7 | 253.9 | 232.66 | 208.58 | 182.73 | 161.28 | 137.14 | 117.78 | 91.1 | 69.26 | 37.58 | 9.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
156 | 14 | 2026-07-25 | 334 | 302.73 | 277.57 | 251.05 | 218.41 | 204.01 | 184.51 | 147.25 | 130.91 | 116.56 | 96.76 | 78.04 | 34.84 | 5.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
157 | 12 | 2026-06-27 | 311 | 268.25 | 251.93 | 233.63 | 218.83 | 185.08 | 166.75 | 130.84 | 105.1 | 83.5 | 52.18 | 24.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
158 | 12 | 2026-06-27 | 282 | 260.44 | 244.69 | 221.33 | 206.93 | 186.02 | 157.22 | 128.1 | 91.62 | 65.22 | 36.52 | 12.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
159 | 11 | 2026-06-13 | 353 | 326.05 | 288.88 | 245.68 | 201.88 | 163.38 | 132.98 | 115.5 | 80.85 | 45.87 | 23.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
160 | 10 | 2026-05-30 | 255 | 237.02 | 216.32 | 195.52 | 153.91 | 124.41 | 103.77 | 76.33 | 42.73 | 18.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
161 | 12 | 2026-06-27 | 350 | 331.1 | 298.16 | 275.12 | 231.92 | 200.24 | 176.84 | 152.4 | 119.4 | 91.35 | 64.4 | 41.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
162 | 14 | 2026-07-25 | 422 | 387.44 | 361.59 | 341.91 | 302.91 | 283.67 | 244.81 | 220.63 | 186.83 | 174.53 | 133.13 | 107.16 | 69.2 | 32.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
163 | 11 | 2026-06-13 | 311 | 276.68 | 245.88 | 207.92 | 185.17 | 145.57 | 122.79 | 97.59 | 70.95 | 39.13 | 14.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
164 | 11 | 2026-06-13 | 330 | 309 | 281.1 | 241.1 | 193.7 | 170.67 | 123.87 | 100.11 | 70.88 | 32.54 | 12.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
165 | 13 | 2026-07-11 | 330 | 305.58 | 279.45 | 252.45 | 236.55 | 213.8 | 178.6 | 144.1 | 112.38 | 88.92 | 66.88 | 39.52 | 9.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
166 | 12 | 2026-06-27 | 306 | 280.72 | 252.84 | 236.5 | 213.55 | 187.09 | 145.49 | 126.29 | 108.31 | 81.01 | 47.41 | 16.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
167 | 14 | 2026-07-25 | 365 | 332.24 | 299.06 | 274.88 | 252.08 | 220.13 | 192.99 | 160.59 | 130.7 | 109.62 | 85.43 | 47.91 | 31.1 | 2.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
168 | 14 | 2026-07-25 | 333 | 317.7 | 290.79 | 266.3 | 237.95 | 218.68 | 181.72 | 152.08 | 115.23 | 102.33 | 77.89 | 58.97 | 25.97 | 5.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
169 | 11 | 2026-06-13 | 270 | 240.32 | 225.8 | 191.78 | 154.34 | 140.7 | 123.36 | 84.6 | 52.35 | 36.51 | 15.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
170 | 12 | 2026-06-27 | 319 | 301.14 | 263.34 | 238.77 | 207.96 | 166.07 | 134.99 | 107.99 | 92.95 | 64.04 | 41.24 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
171 | 9 | 2026-05-16 | 238 | 213.52 | 194.17 | 167.93 | 137.27 | 111.05 | 88.3 | 73.11 | 34.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 14 | 2026-07-25 | 401 | 369.8 | 327.14 | 300.28 | 272.53 | 230.19 | 211.29 | 170.82 | 154.91 | 128.36 | 99.56 | 77.94 | 56.74 | 15.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
173 | 13 | 2026-07-11 | 372 | 346.26 | 310.26 | 285.62 | 240.96 | 210.3 | 192.3 | 157.8 | 130.92 | 100.1 | 72.8 | 40.94 | 15.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
174 | 10 | 2026-05-30 | 247 | 217.89 | 197.65 | 176.23 | 141.44 | 117.24 | 86.69 | 64.99 | 36.93 | 13.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
175 | 15 | 2026-08-08 | 402 | 360.4 | 338.32 | 305.76 | 279.36 | 245.39 | 208.64 | 191.92 | 162.02 | 131.42 | 111.74 | 92.49 | 64.74 | 39.74 | 8.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
176 | 15 | 2026-08-08 | 388 | 364.63 | 342.08 | 306.98 | 282.13 | 265.73 | 228.77 | 204.45 | 180.44 | 161.06 | 126.25 | 91 | 63.4 | 38.4 | 20.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
177 | 9 | 2026-05-16 | 249 | 228.35 | 211.71 | 181.31 | 135.49 | 95.89 | 70.41 | 22.41 | 9.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
178 | 13 | 2026-07-11 | 316 | 285.9 | 250.65 | 229.05 | 204.91 | 179.71 | 158.11 | 137.95 | 107.53 | 90.25 | 47.35 | 30.58 | 11.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
179 | 11 | 2026-06-13 | 276 | 260.32 | 232.37 | 203.77 | 164.5 | 136.44 | 116.2 | 93.42 | 63.04 | 42.98 | 19.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
180 | 14 | 2026-07-25 | 339 | 316.32 | 286.43 | 251.64 | 226.34 | 207.12 | 192.84 | 176.52 | 140.52 | 107.86 | 70.12 | 55.93 | 38.97 | 20.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
181 | 8 | 2026-05-02 | 228 | 182.4 | 144.6 | 113.86 | 86.3 | 56.8 | 30.8 | 9.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
182 | 12 | 2026-06-27 | 297 | 261.3 | 239.74 | 216.78 | 178.38 | 151.08 | 128.85 | 96 | 77.85 | 50.33 | 36.8 | 21.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
183 | 12 | 2026-06-27 | 304 | 284.5 | 261.94 | 234.99 | 206.79 | 175.83 | 150.89 | 131.75 | 91.73 | 69.97 | 49.81 | 8.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
184 | 9 | 2026-05-16 | 254 | 211.52 | 186.32 | 157.25 | 133.46 | 96.96 | 64.1 | 47 | 18.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
185 | 15 | 2026-08-08 | 396 | 372.97 | 355.03 | 332.63 | 291.23 | 270.95 | 246.11 | 200.29 | 173.2 | 144.4 | 120.4 | 77.48 | 57.38 | 40.74 | 4.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
186 | 9 | 2026-05-16 | 237 | 196.19 | 175.52 | 156.65 | 114.3 | 83.58 | 63.69 | 47.19 | 23.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
187 | 13 | 2026-07-11 | 341 | 310.34 | 286.58 | 243.66 | 219.28 | 193.91 | 165.35 | 146.95 | 131.59 | 103.87 | 61.75 | 26.99 | 4.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
188 | 12 | 2026-06-27 | 252 | 225.34 | 207.28 | 192.71 | 165.73 | 140.18 | 123.08 | 100.58 | 82.58 | 48.98 | 25.98 | 3.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
189 | 13 | 2026-07-11 | 337 | 315.56 | 268.36 | 248.98 | 219.48 | 204.78 | 191.58 | 157.98 | 134.06 | 98.55 | 72.55 | 45.6 | 13.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
190 | 15 | 2026-08-08 | 413 | 386.36 | 346.04 | 314.19 | 295.86 | 272.54 | 252.24 | 221.9 | 204.3 | 181.1 | 149.71 | 127.87 | 90.67 | 51.98 | 24.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
191 | 12 | 2026-06-27 | 306 | 276.96 | 239.72 | 218.12 | 191.66 | 168.06 | 154.86 | 132.23 | 100.43 | 80.15 | 47.03 | 29.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
192 | 11 | 2026-06-13 | 271 | 235.28 | 204.17 | 187.4 | 174.8 | 154.7 | 126.18 | 85.48 | 49 | 20.92 | 3.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
193 | 13 | 2026-07-11 | 314 | 286.74 | 266.49 | 229.05 | 200.76 | 180.52 | 145.54 | 106.01 | 87.65 | 65.95 | 45.95 | 21.83 | 5.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
194 | 13 | 2026-07-11 | 313 | 286.48 | 266.74 | 242.98 | 226.58 | 191.79 | 153.83 | 132.76 | 119.23 | 96.79 | 59.94 | 38.86 | 7.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
195 | 10 | 2026-05-30 | 296 | 265.85 | 236.87 | 219.27 | 179.67 | 158.99 | 134.57 | 90.49 | 52.87 | 17.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
196 | 8 | 2026-05-02 | 217 | 193.9 | 153.09 | 132.29 | 102.08 | 61.52 | 46.04 | 19.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
197 | 12 | 2026-06-27 | 308 | 274.61 | 252.11 | 228.11 | 204.02 | 173.42 | 146.78 | 101.18 | 71.78 | 54.14 | 17.96 | 3.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
198 | 15 | 2026-08-08 | 358 | 318.4 | 301.3 | 280.4 | 255.1 | 229.36 | 211.72 | 175.76 | 143.1 | 119.88 | 92.16 | 66.2 | 46.04 | 29.66 | 6.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
199 | 12 | 2026-06-27 | 320 | 281.6 | 260.6 | 224.02 | 196.42 | 171.34 | 147.34 | 117.86 | 91.26 | 54.69 | 33.95 | 8.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
200 | 8 | 2026-05-02 | 217 | 192.5 | 171.59 | 140.39 | 119.89 | 88.09 | 50.29 | 13.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
201 | 10 | 2026-05-30 | 245 | 224.76 | 187.36 | 169.72 | 146.92 | 124.56 | 80.76 | 57.97 | 34.45 | 8.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
202 | 10 | 2026-05-30 | 226 | 198.26 | 184.07 | 171.67 | 151.09 | 121.65 | 76.41 | 51.91 | 33.04 | 7.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
203 | 12 | 2026-06-27 | 301 | 260.53 | 243.88 | 224.61 | 204.52 | 178.2 | 155.8 | 122.2 | 104.26 | 64.22 | 40.7 | 9.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
204 | 15 | 2026-08-08 | 370 | 347.95 | 332.95 | 298.55 | 286.15 | 242.47 | 212.26 | 187.26 | 163.32 | 128.82 | 102.98 | 85.82 | 56.82 | 40.17 | 18.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
205 | 11 | 2026-06-13 | 261 | 234.32 | 212 | 183.19 | 146.27 | 113.82 | 90.06 | 63.11 | 42.95 | 23.75 | 6.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
206 | 12 | 2026-06-27 | 274 | 256 | 218.5 | 188.26 | 167.61 | 152.42 | 126.02 | 88.06 | 69.66 | 41.66 | 24.61 | 5.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
207 | 12 | 2026-06-27 | 322 | 288.12 | 247.65 | 233.71 | 209.79 | 178.11 | 151.86 | 131.71 | 106.33 | 80.68 | 56.6 | 21.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
208 | 11 | 2026-06-13 | 258 | 242.32 | 221.92 | 198.8 | 150.8 | 128.3 | 103.7 | 69.78 | 40.2 | 25.94 | 6.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
209 | 11 | 2026-06-13 | 276 | 242.4 | 207.15 | 179.55 | 154.8 | 132.3 | 107.55 | 79.35 | 55.55 | 32.37 | 11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
210 | 15 | 2026-08-08 | 418 | 386.1 | 369.05 | 344.91 | 327.86 | 293.46 | 265.86 | 224.26 | 199.51 | 170.44 | 123.04 | 106.66 | 75.79 | 37.39 | 14.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
211 | 16 | 2026-08-22 | 387 | 365.55 | 338.76 | 314.71 | 293.39 | 256.43 | 232.23 | 215.91 | 188.55 | 175.65 | 142.71 | 123.99 | 98.49 | 68.85 | 37.53 | 22.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
212 | 14 | 2026-07-25 | 391 | 352.65 | 328.87 | 289.54 | 258.86 | 227.58 | 212.18 | 188.09 | 156.19 | 136.84 | 110.61 | 65.01 | 52.21 | 27.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
213 | 13 | 2026-07-11 | 308 | 271.28 | 245.06 | 224.76 | 195.06 | 171.86 | 148.68 | 127.88 | 105.48 | 87.18 | 65.58 | 49.98 | 17.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
214 | 16 | 2026-08-22 | 416 | 388.07 | 358.39 | 324.51 | 305.95 | 280.96 | 258.18 | 218.76 | 186 | 161.52 | 142.66 | 121.38 | 90.18 | 57.73 | 35.17 | 4.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
215 | 14 | 2026-07-25 | 360 | 323.74 | 299.54 | 279.02 | 250.14 | 229.06 | 206.02 | 182.92 | 158.41 | 138.2 | 104.57 | 69.05 | 31.13 | 15.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
216 | 12 | 2026-06-27 | 309 | 268.4 | 247.6 | 222.96 | 195.4 | 175.4 | 154.6 | 124.6 | 95.72 | 76.48 | 45.7 | 9.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
217 | 13 | 2026-07-11 | 315 | 293.27 | 273.75 | 240.12 | 215.48 | 180.08 | 161 | 135.56 | 123.16 | 93.55 | 61.93 | 41.43 | 21.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
218 | 15 | 2026-08-08 | 324 | 306.52 | 286.92 | 269.72 | 244.87 | 232.07 | 210.37 | 182.29 | 166.65 | 130.17 | 112.67 | 89.17 | 61.67 | 45.92 | 23.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 | 11 | 2026-06-13 | 301 | 280.42 | 261.52 | 235.6 | 216.7 | 176.66 | 139.22 | 98.94 | 67.09 | 38.59 | 17.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220 | 8 | 2026-05-02 | 238 | 209.02 | 180.22 | 155.14 | 126.28 | 96.67 | 68.27 | 31.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
221 | 10 | 2026-05-30 | 248 | 222.16 | 191.8 | 160.84 | 140.49 | 124.51 | 105.95 | 91.1 | 55.91 | 19.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
222 | 14 | 2026-07-25 | 392 | 372.89 | 336.49 | 318.13 | 283.93 | 258.01 | 237.53 | 216.07 | 189.21 | 150.16 | 114.96 | 82.57 | 61.99 | 28.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
223 | 14 | 2026-07-25 | 360 | 334.92 | 318.27 | 289.46 | 267.46 | 242.26 | 225.49 | 192.45 | 168.26 | 131.86 | 118.42 | 79.54 | 41.2 | 15.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
224 | 14 | 2026-07-25 | 354 | 334.53 | 304.89 | 271.61 | 238.55 | 209.75 | 179.39 | 141.05 | 123.42 | 104.04 | 90.71 | 63.21 | 24.81 | 2.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
225 | 11 | 2026-06-13 | 289 | 262.6 | 230.17 | 210.08 | 174.68 | 160.58 | 126.94 | 97.3 | 72.02 | 55 | 12.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
226 | 8 | 2026-05-02 | 216 | 192.22 | 170.72 | 151.12 | 132.67 | 88.87 | 50.37 | 22.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
227 | 12 | 2026-06-27 | 313 | 268.6 | 241.81 | 198.89 | 174.53 | 132.53 | 112.73 | 92.43 | 72.69 | 57.15 | 32.35 | 4.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | 14 | 2026-07-25 | 349 | 331.52 | 302.96 | 270.32 | 246.45 | 228.43 | 205.93 | 175.25 | 152.45 | 119.95 | 101.15 | 65.96 | 42.36 | 12.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | 9 | 2026-05-16 | 246 | 222.9 | 197.3 | 158.9 | 129.2 | 106.7 | 82.1 | 59.3 | 24.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | 12 | 2026-06-27 | 293 | 272.48 | 245.96 | 210.08 | 180.58 | 151.72 | 124.69 | 100.77 | 81.03 | 61.31 | 30.76 | 7.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | 14 | 2026-07-25 | 355 | 336.6 | 292.2 | 268.44 | 248.66 | 224.46 | 191.6 | 166.08 | 139.98 | 113.58 | 85.02 | 66.47 | 46.31 | 17.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | 10 | 2026-05-30 | 269 | 245.6 | 228.94 | 191.02 | 166.54 | 144.1 | 118.55 | 89.99 | 59.25 | 21.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233 | 12 | 2026-06-27 | 314 | 289.36 | 263.76 | 221.28 | 198.88 | 170.38 | 141.58 | 116.21 | 80.33 | 47.99 | 23.61 | 5.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
234 | 10 | 2026-05-30 | 258 | 231 | 216.48 | 188.48 | 173.76 | 141.96 | 117.05 | 82.25 | 65.45 | 30.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
235 | 10 | 2026-05-30 | 258 | 225.5 | 195.5 | 176.6 | 140.41 | 112.09 | 97.04 | 78.16 | 35.56 | 11.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
236 | 12 | 2026-06-27 | 277 | 242.68 | 199.61 | 176.25 | 156.36 | 130.62 | 112.42 | 91.07 | 61.91 | 36.95 | 21.95 | 1.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
237 | 11 | 2026-06-13 | 259 | 235.54 | 206.47 | 182.67 | 151.71 | 125.97 | 102.6 | 81.48 | 66.18 | 39.5 | 17.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
238 | 9 | 2026-05-16 | 237 | 218.67 | 195.24 | 168.45 | 140.91 | 120.11 | 76.45 | 52.33 | 33.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
239 | 11 | 2026-06-13 | 311 | 294.83 | 262.85 | 248.5 | 210.8 | 182.66 | 159.46 | 122.29 | 88.32 | 61.64 | 34.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
240 | 14 | 2026-07-25 | 331 | 317.06 | 294.5 | 271.18 | 238.18 | 210.82 | 175.12 | 159.82 | 137.86 | 110.72 | 82.25 | 56 | 39.28 | 18.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
241 | 13 | 2026-07-11 | 366 | 350.42 | 313.46 | 279.96 | 252.6 | 222.26 | 193.22 | 167.67 | 140.07 | 108.25 | 71.29 | 43.75 | 7.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
242 | 10 | 2026-05-30 | 278 | 264.56 | 236.16 | 195.08 | 164.34 | 139.94 | 105.84 | 77.34 | 52.56 | 24.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
243 | 11 | 2026-06-13 | 319 | 283.64 | 255.44 | 226.64 | 197.64 | 169.52 | 146.42 | 107.56 | 88.75 | 59.89 | 40.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | 11 | 2026-06-13 | 314 | 283.98 | 254.37 | 225.37 | 197.83 | 156.03 | 129 | 92.28 | 72.07 | 26.83 | 1.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 15 | 2026-08-08 | 405 | 381.96 | 354.36 | 332.35 | 292.75 | 257.65 | 237.35 | 203.35 | 180.55 | 153.75 | 129.25 | 103.07 | 81.06 | 53.06 | 19.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
246 | 14 | 2026-07-25 | 382 | 347.83 | 322.28 | 303.03 | 275.99 | 248.69 | 217.41 | 200.69 | 174.29 | 142.93 | 100.45 | 74.89 | 43.04 | 6.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
247 | 12 | 2026-06-27 | 314 | 276.08 | 253.36 | 237.19 | 209.1 | 176.06 | 159.04 | 122.78 | 79.58 | 56.02 | 35.72 | 14.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
248 | 10 | 2026-05-30 | 293 | 264.68 | 246.35 | 219.32 | 187.16 | 155.96 | 114.92 | 77.48 | 47.66 | 24.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
249 | 14 | 2026-07-25 | 359 | 326.6 | 307.74 | 285.69 | 268.95 | 228.8 | 203.18 | 178.68 | 151.08 | 135.58 | 108.49 | 80.93 | 58.53 | 24.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
250 | 9 | 2026-05-16 | 235 | 202.44 | 173.04 | 145.48 | 115.14 | 93.14 | 65.76 | 35.23 | 5.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
251 | 11 | 2026-06-13 | 262 | 233.4 | 208.98 | 187.7 | 150.07 | 133.73 | 112.53 | 88.85 | 70.49 | 40.81 | 8.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 11 | 2026-06-13 | 353 | 309.2 | 284.42 | 244.13 | 214.63 | 196.33 | 161.77 | 118.27 | 87 | 55.28 | 31.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
253 | 13 | 2026-07-11 | 308 | 284.5 | 251.39 | 227.45 | 199.13 | 161.53 | 145.15 | 125.8 | 95.64 | 75.24 | 48.64 | 26.54 | 8.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
254 | 10 | 2026-05-30 | 256 | 221.8 | 189.32 | 167.72 | 137.12 | 101.57 | 76.58 | 61.62 | 42.15 | 14.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
255 | 14 | 2026-07-25 | 371 | 345.63 | 316.03 | 283.09 | 256.69 | 234.85 | 201.46 | 167.14 | 139.62 | 117.57 | 84.57 | 50.97 | 32.91 | 7.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
256 | 12 | 2026-06-27 | 317 | 282.32 | 239.25 | 209.99 | 185.14 | 154.54 | 130.34 | 92.15 | 54.23 | 36.6 | 20.6 | 6.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
257 | 16 | 2026-08-22 | 364 | 347.57 | 330.07 | 302.79 | 284.73 | 261.33 | 249.03 | 225.51 | 189.87 | 164.22 | 144.38 | 126.02 | 90.82 | 72.37 | 43.46 | 7.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
258 | 11 | 2026-06-13 | 279 | 237.92 | 219.11 | 193.7 | 178.66 | 165.02 | 138.42 | 118.62 | 100.58 | 74.66 | 38.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
259 | 13 | 2026-07-11 | 318 | 293.52 | 260.41 | 226.24 | 203.14 | 182.9 | 145.77 | 124.04 | 94.78 | 75.28 | 55.84 | 30.1 | 10.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
260 | 14 | 2026-07-25 | 376 | 350.08 | 324.12 | 285.72 | 253.32 | 229.56 | 195.96 | 179.04 | 152.04 | 129.25 | 96.57 | 68.07 | 39.16 | 13.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
261 | 13 | 2026-07-11 | 312 | 268.8 | 244.48 | 209.38 | 193.06 | 169.38 | 127.78 | 106.33 | 89.31 | 74.14 | 58.24 | 33.74 | 16.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
262 | 12 | 2026-06-27 | 296 | 269.87 | 243.41 | 215.69 | 176.16 | 139.97 | 114.17 | 96.17 | 63.49 | 39.34 | 25.48 | 8.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
263 | 13 | 2026-07-11 | 323 | 290.75 | 274.55 | 251.03 | 228.77 | 189.83 | 167.47 | 147.47 | 120.52 | 81.81 | 63.11 | 40.79 | 17.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
264 | 14 | 2026-07-25 | 363 | 340.32 | 326.13 | 308.58 | 275.75 | 253.75 | 229.18 | 199.54 | 158.1 | 125.7 | 99.63 | 75.15 | 49.59 | 7.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
265 | 12 | 2026-06-27 | 329 | 302.78 | 282.08 | 260.63 | 237.38 | 198.05 | 170.12 | 130.92 | 91.72 | 64 | 40.5 | 20.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
266 | 11 | 2026-06-13 | 261 | 236.6 | 207.74 | 185.69 | 163.99 | 129.77 | 94.43 | 72.73 | 58.97 | 36.17 | 12.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
267 | 14 | 2026-07-25 | 364 | 328.16 | 306.16 | 276.96 | 249.4 | 222.4 | 197.44 | 177.04 | 154.48 | 130.72 | 106.54 | 79.4 | 39.8 | 6.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
268 | 11 | 2026-06-13 | 279 | 252.82 | 227.86 | 203.66 | 180.72 | 149.98 | 134.02 | 94.52 | 64.88 | 36.07 | 19.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
269 | 10 | 2026-05-30 | 262 | 238 | 203.78 | 177.94 | 152.48 | 127.02 | 96.34 | 62.26 | 23.57 | 4.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
270 | 12 | 2026-06-27 | 279 | 263.88 | 245.88 | 224.76 | 202.26 | 184.62 | 159.78 | 127.86 | 102.4 | 66.89 | 42.89 | 18.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
271 | 12 | 2026-06-27 | 301 | 262.5 | 237.8 | 214.84 | 184.92 | 164.01 | 141.69 | 119.46 | 94.38 | 56.98 | 30.1 | 12.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
272 | 13 | 2026-07-11 | 382 | 356.44 | 313.52 | 285.1 | 265.36 | 239.62 | 220.58 | 197.12 | 155.78 | 132.74 | 90.14 | 45.14 | 14.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
273 | 10 | 2026-05-30 | 267 | 228.72 | 202.5 | 178.49 | 163.45 | 143.65 | 105.25 | 73.9 | 42.54 | 10.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
274 | 16 | 2026-08-22 | 394 | 361.15 | 333.59 | 306.31 | 284.11 | 263.37 | 237.27 | 195.4 | 154.1 | 124.94 | 100.16 | 84.99 | 61.62 | 38.31 | 19.5 | 4.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
275 | 12 | 2026-06-27 | 297 | 259.87 | 238.45 | 217.33 | 195.29 | 168.43 | 145.81 | 118.12 | 95.08 | 72.82 | 54.58 | 22.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
276 | 14 | 2026-07-25 | 334 | 307.54 | 290.44 | 257.59 | 225.99 | 206.39 | 182.38 | 161.98 | 134.84 | 112.58 | 89.02 | 54.85 | 36.05 | 18.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
277 | 11 | 2026-06-13 | 315 | 282.66 | 260.61 | 214.41 | 199.24 | 179.46 | 147.78 | 105.98 | 63.98 | 45.92 | 14.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
278 | 12 | 2026-06-27 | 304 | 268.66 | 247.92 | 227.57 | 196.41 | 162.66 | 138.72 | 113.71 | 91.21 | 74.41 | 46.41 | 19.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
279 | 11 | 2026-06-13 | 312 | 286.45 | 250.45 | 225.75 | 194.13 | 167.81 | 139.43 | 98.73 | 69.87 | 43.83 | 16.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
280 | 12 | 2026-06-27 | 321 | 278.66 | 255.29 | 231.77 | 208.65 | 177.45 | 142.89 | 125.03 | 87.29 | 64.26 | 45.02 | 18.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
281 | 12 | 2026-06-27 | 357 | 326.5 | 283.9 | 249.1 | 206.35 | 182.89 | 161.89 | 122.67 | 95.67 | 59.07 | 33.33 | 4.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
282 | 15 | 2026-08-08 | 395 | 370.22 | 343.82 | 306.69 | 272.19 | 247.44 | 222.44 | 201.74 | 169.4 | 142.36 | 112.12 | 74.04 | 56.34 | 30.74 | 8.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
283 | 14 | 2026-07-25 | 389 | 354.19 | 322.91 | 291.17 | 265.79 | 239.96 | 202.79 | 168.23 | 144.91 | 119.95 | 103.15 | 65.39 | 41.93 | 20.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
284 | 8 | 2026-05-02 | 231 | 193.8 | 163.46 | 137.14 | 108.72 | 81.63 | 50.89 | 16.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
285 | 13 | 2026-07-11 | 355 | 333.68 | 308.38 | 275.72 | 248.42 | 231.68 | 194.24 | 155.74 | 133.34 | 95.72 | 73.32 | 55.65 | 24.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
286 | 11 | 2026-06-13 | 269 | 245.69 | 221.93 | 197.75 | 179.03 | 160.31 | 135.82 | 101.01 | 75.48 | 49.2 | 11.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
287 | 12 | 2026-06-27 | 316 | 288.46 | 257.74 | 244.41 | 221.09 | 184.59 | 146.89 | 114.64 | 92.68 | 62.52 | 41.73 | 26.13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
288 | 9 | 2026-05-16 | 267 | 236.85 | 210.63 | 183.59 | 143.44 | 116.41 | 89.5 | 68.62 | 29.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
289 | 11 | 2026-06-13 | 272 | 239.34 | 214.26 | 181.62 | 159.54 | 122.42 | 106.3 | 85.66 | 58.52 | 35.42 | 8.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
290 | 9 | 2026-05-16 | 225 | 200.36 | 183.08 | 158.09 | 124.65 | 99.8 | 57.46 | 37.51 | 10.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
291 | 11 | 2026-06-13 | 269 | 234.2 | 214.48 | 199.31 | 168.89 | 151.22 | 117.47 | 87.23 | 58.91 | 29.27 | 4.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
292 | 13 | 2026-07-11 | 355 | 329.8 | 292.68 | 266.02 | 237.73 | 210.82 | 198.22 | 160.62 | 137.42 | 114.38 | 79.1 | 53.2 | 11.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
293 | 13 | 2026-07-11 | 296 | 272 | 256.04 | 242.54 | 228.46 | 202.61 | 177.41 | 149.41 | 106.21 | 88.73 | 61.37 | 27.77 | 7.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | 14 | 2026-07-25 | 337 | 313.03 | 288.07 | 247.27 | 233.08 | 208.44 | 194.16 | 163.95 | 135.04 | 117.7 | 104.99 | 65.72 | 35.38 | 16.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
295 | 12 | 2026-06-27 | 342 | 327.04 | 305.21 | 262.09 | 240.08 | 199.37 | 183.03 | 149.39 | 132.58 | 97.6 | 58.6 | 39.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
296 | 11 | 2026-06-13 | 276 | 260.1 | 234.09 | 198.25 | 183.55 | 155.47 | 131.77 | 93.58 | 68.83 | 47.41 | 7.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
297 | 13 | 2026-07-11 | 292 | 268.44 | 243.64 | 223.5 | 206.85 | 189.69 | 155.52 | 132.09 | 110.67 | 79.99 | 62.39 | 35.44 | 12.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
298 | 15 | 2026-08-08 | 368 | 336.89 | 311.81 | 290.05 | 267.26 | 239.54 | 216.02 | 180.62 | 159.02 | 144.62 | 122.66 | 103.52 | 72.32 | 44.58 | 24.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
299 | 12 | 2026-06-27 | 297 | 252.76 | 227.56 | 192.46 | 176.78 | 163.02 | 124.02 | 100.37 | 80.37 | 57.6 | 42.48 | 26.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
300 | 9 | 2026-05-16 | 245 | 226.55 | 200.93 | 172.81 | 147.61 | 122.79 | 95.06 | 56.3 | 33.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
301 | 11 | 2026-06-13 | 289 | 271 | 244.78 | 205.34 | 172.51 | 140.91 | 124.59 | 86.51 | 69.71 | 41.63 | 18.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
302 | 14 | 2026-07-25 | 360 | 344.1 | 316.74 | 294.6 | 271.35 | 246.15 | 217.15 | 199.29 | 159.54 | 135.67 | 107.2 | 87.42 | 54.42 | 30.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
303 | 14 | 2026-07-25 | 326 | 310.42 | 292.79 | 252.89 | 230.17 | 200.67 | 173.23 | 142.21 | 124.81 | 107.59 | 72.94 | 49.54 | 32.05 | 9.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
304 | 9 | 2026-05-16 | 242 | 203.6 | 175.87 | 129.67 | 105.58 | 81.07 | 64.26 | 49.5 | 28.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
305 | 9 | 2026-05-16 | 245 | 221.24 | 177.74 | 149.24 | 123.23 | 95.54 | 75.38 | 56.5 | 34.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
306 | 14 | 2026-07-25 | 362 | 342.2 | 316.68 | 282.6 | 259.38 | 241.98 | 217.8 | 195.8 | 160.29 | 135.5 | 113.6 | 72.2 | 40.71 | 8.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
307 | 12 | 2026-06-27 | 305 | 273.08 | 249.16 | 215.88 | 194.15 | 172.8 | 152.64 | 124.48 | 108.64 | 84.67 | 57.72 | 25.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
308 | 11 | 2026-06-13 | 278 | 263.3 | 228.8 | 199.1 | 175.3 | 157.36 | 130.71 | 86.82 | 63.42 | 28.04 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
309 | 11 | 2026-06-13 | 326 | 305 | 276.2 | 247.4 | 220.6 | 179.02 | 155.62 | 137.22 | 110.98 | 82.98 | 37.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
310 | 12 | 2026-06-27 | 276 | 254.16 | 227.64 | 200.76 | 178.68 | 145.85 | 127.05 | 103.95 | 72.75 | 53.01 | 31.62 | 7.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
311 | 12 | 2026-06-27 | 300 | 265.5 | 244.2 | 217.8 | 189 | 161.97 | 145.77 | 128.17 | 85.25 | 61.07 | 26.75 | 9.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
312 | 11 | 2026-06-13 | 237 | 220.66 | 193.06 | 163.91 | 136.47 | 105.42 | 88.62 | 60.62 | 43.23 | 25.31 | 3.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
313 | 12 | 2026-06-27 | 318 | 281.28 | 259.83 | 245.43 | 222.49 | 178.81 | 153.46 | 109.8 | 94.29 | 70.79 | 48.24 | 25.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
314 | 13 | 2026-07-11 | 352 | 325.05 | 294.09 | 273.79 | 251.24 | 222.64 | 195.6 | 172 | 138.82 | 94.74 | 63.66 | 21.31 | 4.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
315 | 11 | 2026-06-13 | 338 | 306.61 | 289.81 | 252.19 | 220.99 | 180.19 | 158.59 | 120.11 | 99.04 | 64.25 | 17.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
316 | 14 | 2026-07-25 | 369 | 347.24 | 315.32 | 275.03 | 251.09 | 227.63 | 205.19 | 160.39 | 130.5 | 109.08 | 85.43 | 60.68 | 32.52 | 6.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
317 | 17 | 2026-09-05 | 404 | 375.88 | 344.68 | 322.9 | 298.26 | 282.35 | 263.08 | 236.2 | 213.65 | 187.1 | 158.03 | 128.39 | 101.71 | 83.65 | 62.93 | 48.23 | 9.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
318 | 10 | 2026-05-30 | 255 | 234.65 | 204.55 | 171.27 | 144.99 | 116.08 | 87.76 | 73.06 | 50.86 | 7.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 11 | 2026-06-13 | 297 | 263.4 | 237.96 | 217.46 | 178.52 | 146.04 | 126.44 | 97.37 | 77.65 | 45.73 | 14.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
320 | 10 | 2026-05-30 | 302 | 275.78 | 229.17 | 203.07 | 171.07 | 124.87 | 108.21 | 77.47 | 44.61 | 22.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
321 | 12 | 2026-06-27 | 363 | 331.89 | 298.74 | 258.99 | 227.64 | 198.66 | 163.38 | 141.78 | 127.21 | 88.01 | 47.81 | 15.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
322 | 18 | 2026-09-19 | 420 | 396.68 | 364.78 | 344.57 | 325.66 | 298.38 | 277.26 | 260.34 | 237.54 | 200.41 | 171.29 | 146.49 | 129.29 | 110.81 | 91.49 | 67.37 | 40.46 | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
323 | 11 | 2026-06-13 | 256 | 222.85 | 196.35 | 166.26 | 145.35 | 118.37 | 86.04 | 64.14 | 45.66 | 16.68 | 1.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
324 | 10 | 2026-05-30 | 276 | 239.08 | 201.98 | 165.06 | 146.93 | 131.63 | 99.95 | 73.99 | 45.99 | 26.99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
325 | 13 | 2026-07-11 | 350 | 313.79 | 282.63 | 242.88 | 227.38 | 206.31 | 185.01 | 150.69 | 129.3 | 103.7 | 64.28 | 40.28 | 11.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
326 | 13 | 2026-07-11 | 288 | 272.95 | 252.79 | 221.83 | 182.41 | 144.22 | 116.22 | 98.73 | 76.1 | 54.65 | 37.1 | 23.1 | 1.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
327 | 13 | 2026-07-11 | 355 | 331.2 | 308.48 | 282.92 | 253.16 | 212.12 | 189.16 | 157 | 136.9 | 110.72 | 83.07 | 50.22 | 30.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
328 | 13 | 2026-07-11 | 301 | 280.6 | 258.06 | 233.56 | 205.4 | 190.7 | 152.62 | 122.53 | 97.11 | 76.43 | 53.25 | 34.01 | 2.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
329 | 10 | 2026-05-30 | 269 | 243.1 | 202.4 | 178.43 | 149.63 | 132.35 | 100.75 | 59.71 | 36.19 | 9.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
330 | 13 | 2026-07-11 | 372 | 354.84 | 325.17 | 302.07 | 257.41 | 222.65 | 195.77 | 170.97 | 138.63 | 116.37 | 91.93 | 53.65 | 31.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
331 | 16 | 2026-08-22 | 350 | 334.88 | 318.48 | 285.58 | 271.18 | 258.06 | 236.91 | 210.67 | 187.63 | 161.41 | 141.32 | 119.93 | 90.81 | 65.61 | 33.69 | 5.81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
332 | 11 | 2026-06-13 | 334 | 313.84 | 282.45 | 236.85 | 208.43 | 181.07 | 142.57 | 112.65 | 85.97 | 48.85 | 18.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
333 | 11 | 2026-06-13 | 299 | 274.25 | 251.69 | 210.89 | 178.99 | 152.99 | 123.73 | 97.89 | 74.11 | 35.95 | 15.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
334 | 15 | 2026-08-08 | 383 | 356.36 | 327.12 | 305.88 | 291.53 | 264.33 | 244.17 | 220.2 | 182.7 | 153.18 | 115.74 | 96.84 | 72.76 | 34.96 | 9.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
335 | 11 | 2026-06-13 | 251 | 228.86 | 197.06 | 177.45 | 139.49 | 112.49 | 94.47 | 72.27 | 46.09 | 32.49 | 16.49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
336 | 8 | 2026-05-02 | 278 | 259.1 | 236.06 | 193.4 | 148.16 | 108.12 | 64.67 | 19.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
337 | 15 | 2026-08-08 | 365 | 347.37 | 321.45 | 300.33 | 269.55 | 241.13 | 221.88 | 196.26 | 173.9 | 139.18 | 102.6 | 79.5 | 48.14 | 25.59 | 9.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
338 | 12 | 2026-06-27 | 288 | 252.48 | 231.83 | 202.58 | 181.38 | 159.54 | 139.48 | 113.83 | 90.23 | 73.51 | 45.43 | 14.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
339 | 11 | 2026-06-13 | 245 | 222.32 | 201.32 | 175.8 | 154.74 | 132.3 | 109.26 | 82.98 | 54.9 | 36.75 | 16.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
340 | 11 | 2026-06-13 | 294 | 260.42 | 238.19 | 205.13 | 172.45 | 147.25 | 121.95 | 100.35 | 84.6 | 63.8 | 21.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
341 | 10 | 2026-05-30 | 286 | 267.52 | 247.72 | 224.12 | 185.36 | 145.92 | 100.32 | 65.53 | 33.61 | 10.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 17 | 2026-09-05 | 399 | 371 | 346.06 | 315.85 | 289.25 | 272.03 | 234.8 | 217.4 | 196.1 | 168.82 | 134.01 | 110.36 | 89.48 | 70.76 | 54.59 | 36.14 | 18.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
343 | 13 | 2026-07-11 | 294 | 272.44 | 256.04 | 235.79 | 215.54 | 193.53 | 161.67 | 132.43 | 109.07 | 81.81 | 46.11 | 25.46 | 5.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
344 | 10 | 2026-05-30 | 283 | 257.52 | 225.57 | 194.21 | 155.45 | 139.64 | 117.68 | 89.84 | 51.84 | 18.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
345 | 10 | 2026-05-30 | 247 | 226.84 | 211.64 | 184.69 | 158.47 | 119.97 | 85.77 | 68.49 | 53.49 | 24.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
346 | 11 | 2026-06-13 | 362 | 326.45 | 299.45 | 265.85 | 227.6 | 195.6 | 179.85 | 145.4 | 105.12 | 63.25 | 40.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
347 | 16 | 2026-08-22 | 374 | 358.1 | 344.9 | 318.02 | 294.17 | 271.22 | 245.3 | 213.44 | 197.84 | 181.46 | 152.3 | 117.62 | 93.12 | 54.43 | 36.23 | 10.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
348 | 11 | 2026-06-13 | 261 | 243 | 219 | 194.5 | 173.71 | 156.51 | 140.31 | 102.12 | 58.32 | 28.07 | 9.17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
349 | 16 | 2026-08-22 | 392 | 372.76 | 355.27 | 328.27 | 285.37 | 266.77 | 235.27 | 215.55 | 199.15 | 175.5 | 148.2 | 130.57 | 99.97 | 65.87 | 26.67 | 12.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
350 | 16 | 2026-08-22 | 409 | 383.15 | 346.4 | 327.48 | 303.96 | 281.46 | 240.9 | 220.32 | 195.12 | 165.92 | 143.92 | 106.32 | 72.88 | 59.68 | 26.62 | 6.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
351 | 9 | 2026-05-16 | 278 | 243.6 | 207.88 | 162.85 | 145.65 | 104.84 | 72.45 | 50.61 | 23.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
352 | 10 | 2026-05-30 | 217 | 176.5 | 158.5 | 138.7 | 110.2 | 89.99 | 67.94 | 43.75 | 16.03 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
353 | 12 | 2026-06-27 | 354 | 331.74 | 291.99 | 265.99 | 235.25 | 191.8 | 165.95 | 137.43 | 97.39 | 78.48 | 38.28 | 14.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
354 | 14 | 2026-07-25 | 378 | 363.2 | 335.36 | 312.73 | 298.21 | 263.89 | 224.47 | 202.24 | 183.37 | 139.57 | 104.07 | 67.41 | 40.55 | 20.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
355 | 11 | 2026-06-13 | 276 | 247.44 | 229.89 | 201.39 | 177.39 | 137.11 | 117.31 | 86.91 | 62.79 | 36.87 | 1.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
356 | 13 | 2026-07-11 | 345 | 321.55 | 299.79 | 269.29 | 232.63 | 212.83 | 190.03 | 165.24 | 151.6 | 121.67 | 83.03 | 60.03 | 35.07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
357 | 15 | 2026-08-08 | 354 | 323.62 | 301.18 | 269.32 | 246.92 | 231.92 | 209.83 | 187.57 | 160.77 | 133.98 | 105.51 | 82.11 | 57.36 | 35.28 | 16.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
358 | 10 | 2026-05-30 | 234 | 213.79 | 179.57 | 158.66 | 135.66 | 95.9 | 77.9 | 54.05 | 28.52 | 4.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
359 | 13 | 2026-07-11 | 291 | 267.08 | 246.99 | 213.93 | 195.38 | 167.54 | 149.52 | 136.4 | 110 | 88.55 | 48.65 | 27.2 | 6.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
360 | 14 | 2026-07-25 | 323 | 286.7 | 265.35 | 249.23 | 226.68 | 200.72 | 179.22 | 152.22 | 138.78 | 115.13 | 84.89 | 62.89 | 44.41 | 12.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
361 | 9 | 2026-05-16 | 236 | 218.61 | 203.31 | 180.77 | 145.67 | 100.07 | 70.55 | 42.03 | 7.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
362 | 12 | 2026-06-27 | 275 | 251.03 | 212.84 | 194.14 | 173.46 | 151.53 | 115.49 | 80.09 | 55.15 | 31.3 | 15.39 | 0.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
363 | 10 | 2026-05-30 | 305 | 260.76 | 236.61 | 201.25 | 168.14 | 138.94 | 104.26 | 74.26 | 35.26 | 7.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
364 | 15 | 2026-08-08 | 356 | 328.86 | 304.37 | 278.12 | 251.46 | 229.02 | 200.04 | 184.13 | 146.96 | 132.39 | 112.18 | 72.4 | 53.02 | 35.16 | 4.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
365 | 12 | 2026-06-27 | 287 | 258.12 | 229.98 | 206.76 | 182.76 | 168.81 | 146.8 | 111.08 | 90.17 | 51.48 | 37.84 | 14.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
366 | 11 | 2026-06-13 | 281 | 248.76 | 231.06 | 208.92 | 185.74 | 145.04 | 109.94 | 78.2 | 52.7 | 31.58 | 11.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
367 | 15 | 2026-08-08 | 419 | 403.83 | 364.39 | 340.63 | 322.99 | 295.73 | 270.79 | 236.87 | 203.23 | 174.81 | 162.1 | 115.7 | 91.76 | 69.62 | 37.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
368 | 15 | 2026-08-08 | 359 | 334.62 | 313.02 | 283.38 | 263.22 | 222.94 | 204.58 | 189.58 | 157.19 | 134.75 | 104.51 | 80.32 | 54.22 | 29.72 | 1.16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
369 | 13 | 2026-07-11 | 334 | 305.02 | 271.72 | 247.58 | 226.23 | 190.98 | 166.18 | 147.04 | 129.99 | 88.19 | 70.97 | 51.7 | 26.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
370 | 13 | 2026-07-11 | 324 | 283.71 | 260.46 | 241.35 | 222.15 | 195.12 | 175.9 | 148.06 | 108.02 | 87.89 | 69.17 | 39.53 | 6.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
371 | 13 | 2026-07-11 | 317 | 283.46 | 261.1 | 235.3 | 206.32 | 189.32 | 153.57 | 121.17 | 104.21 | 82.51 | 51.01 | 25.04 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
372 | 12 | 2026-06-27 | 295 | 268.82 | 239.34 | 213.58 | 181.9 | 156 | 123.75 | 105.73 | 85.45 | 60.25 | 42.65 | 27.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
373 | 9 | 2026-05-16 | 270 | 237.55 | 205.65 | 168.39 | 142.84 | 104.36 | 68.1 | 42.45 | 5.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
374 | 12 | 2026-06-27 | 272 | 254.78 | 214.63 | 192.55 | 166.75 | 142.26 | 114.14 | 89.15 | 66.05 | 45.55 | 25.2 | 8.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
375 | 11 | 2026-06-13 | 304 | 262 | 243.55 | 221.13 | 192.33 | 161.52 | 139.38 | 103.39 | 62.92 | 41.8 | 11.14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
376 | 11 | 2026-06-13 | 246 | 225.48 | 206.57 | 191.52 | 166.52 | 129.29 | 106.34 | 80.09 | 61.19 | 38.69 | 15.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
377 | 13 | 2026-07-11 | 294 | 274.89 | 253.43 | 233.67 | 206.17 | 190.69 | 172.99 | 137.71 | 117.41 | 99.77 | 79.53 | 40 | 16.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
378 | 14 | 2026-07-25 | 407 | 370 | 346.6 | 313.05 | 273.55 | 244.57 | 213.82 | 192.2 | 173.3 | 149.38 | 126.28 | 102.2 | 63.8 | 33.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
379 | 14 | 2026-07-25 | 342 | 312.74 | 291.65 | 249.76 | 233.12 | 206.62 | 179.94 | 160.34 | 134.93 | 110.18 | 90.04 | 64.3 | 39.48 | 16.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
380 | 10 | 2026-05-30 | 271 | 251.16 | 211.38 | 187.02 | 151.18 | 111.22 | 90.94 | 69.62 | 45.7 | 11.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
381 | 12 | 2026-06-27 | 382 | 362.32 | 331.58 | 297.7 | 260.08 | 242.58 | 212.55 | 170.55 | 133.89 | 115.69 | 74.09 | 27.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
382 | 14 | 2026-07-25 | 369 | 346.96 | 313.48 | 278.48 | 258.88 | 223.5 | 188.22 | 154.25 | 130.25 | 106.73 | 75.77 | 51.13 | 29.71 | 4.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
383 | 10 | 2026-05-30 | 228 | 202.08 | 188.13 | 166.53 | 146.29 | 118.24 | 96.79 | 75.79 | 51.59 | 18.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
384 | 11 | 2026-06-13 | 275 | 252.12 | 227.61 | 201.87 | 183.01 | 167.05 | 135.66 | 108.46 | 75.7 | 35.55 | 14.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
385 | 9 | 2026-05-16 | 223 | 197.5 | 177.7 | 154.98 | 120.68 | 101.82 | 87.2 | 45.95 | 20.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
386 | 14 | 2026-07-25 | 331 | 300.04 | 283.54 | 252.74 | 225.02 | 202.47 | 187.75 | 174.55 | 151.03 | 118.64 | 95.04 | 60.84 | 28.6 | 1.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
387 | 13 | 2026-07-11 | 352 | 332.92 | 304.04 | 264.52 | 239.53 | 205.23 | 188.85 | 146.1 | 119.3 | 92.9 | 65.6 | 34.8 | 2.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
388 | 11 | 2026-06-13 | 304 | 260 | 233.12 | 208.74 | 188.61 | 157.81 | 130.95 | 95.45 | 63.11 | 36.16 | 20.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
389 | 13 | 2026-07-11 | 337 | 310.77 | 294.13 | 270.91 | 242.1 | 219.55 | 176.65 | 150.1 | 123.58 | 79.69 | 53.23 | 19.19 | 1.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
390 | 14 | 2026-07-25 | 387 | 360.6 | 334.42 | 315.5 | 282.32 | 247.76 | 227.67 | 203.53 | 170.53 | 142.53 | 119.43 | 104.73 | 59.49 | 32.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
391 | 11 | 2026-06-13 | 328 | 292.58 | 270.58 | 235.24 | 197.74 | 175.34 | 148.7 | 115.55 | 84.2 | 46.2 | 6.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
392 | 15 | 2026-08-08 | 354 | 332.1 | 317.75 | 290.3 | 270.06 | 256.94 | 229.8 | 202.71 | 166.83 | 130.11 | 108 | 84.08 | 62.62 | 44.14 | 16.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
393 | 11 | 2026-06-13 | 329 | 282.2 | 255.88 | 227.68 | 204.65 | 164.45 | 138.05 | 116.43 | 76.43 | 50.03 | 20.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
394 | 10 | 2026-05-30 | 265 | 244.09 | 224.59 | 201.59 | 159.11 | 126.43 | 96.85 | 74.06 | 50.12 | 31.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
395 | 9 | 2026-05-16 | 234 | 210.6 | 165 | 129 | 111.18 | 86.4 | 66.15 | 42.28 | 19.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
396 | 11 | 2026-06-13 | 279 | 238.3 | 218.17 | 194.17 | 158.17 | 141.74 | 124.46 | 99.16 | 74.17 | 45.01 | 8.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
397 | 11 | 2026-06-13 | 288 | 274 | 248.99 | 211.23 | 178.75 | 147.55 | 123.46 | 101.1 | 69.61 | 40.7 | 9.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
398 | 15 | 2026-08-08 | 366 | 339.45 | 326.43 | 305.23 | 279.05 | 248.9 | 222.68 | 190.23 | 163.23 | 132.03 | 95.55 | 72.45 | 57.57 | 43.29 | 16.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
399 | 14 | 2026-07-25 | 360 | 342.32 | 311.08 | 281.97 | 258.96 | 212.76 | 178.45 | 150.07 | 122.07 | 108.27 | 79.77 | 52.05 | 26.68 | 4.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
400 | 13 | 2026-07-11 | 344 | 327.34 | 309.04 | 281.74 | 254.24 | 225.54 | 196.98 | 169.62 | 139.41 | 106.56 | 89.92 | 58.43 | 28.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
401 | 11 | 2026-06-13 | 314 | 287.4 | 261.78 | 228.78 | 189.36 | 157.36 | 133.39 | 106.36 | 83.8 | 51.94 | 10.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
402 | 14 | 2026-07-25 | 341 | 314.21 | 293.05 | 271.97 | 241.44 | 227.25 | 184.13 | 166.13 | 143.63 | 119.98 | 98.05 | 67.55 | 44.37 | 15.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
403 | 13 | 2026-07-11 | 339 | 302.81 | 276.49 | 255.07 | 229.22 | 215.14 | 183.57 | 148.21 | 126.45 | 108.82 | 78.48 | 46 | 15.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
404 | 11 | 2026-06-13 | 276 | 247.38 | 205.94 | 172.5 | 159.7 | 137.69 | 113.69 | 84.11 | 60.35 | 33.95 | 0.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
405 | 14 | 2026-07-25 | 323 | 294.8 | 278.15 | 256.14 | 243.43 | 222.73 | 189.13 | 161.59 | 131.21 | 98.17 | 79.88 | 46.76 | 28.36 | 1.56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
406 | 15 | 2026-08-08 | 347 | 330.2 | 299.45 | 280.83 | 261.39 | 242.49 | 213.09 | 186.09 | 150.18 | 124.21 | 98.83 | 83.25 | 61.95 | 28.35 | 3.15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
407 | 16 | 2026-08-22 | 378 | 360.45 | 335.7 | 311.69 | 290.61 | 271.29 | 247.98 | 203.9 | 178.4 | 158.56 | 135.53 | 113.87 | 93.63 | 71.55 | 52.28 | 11.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
408 | 12 | 2026-06-27 | 285 | 258.48 | 231.6 | 214.44 | 185.21 | 163.25 | 142.05 | 114.45 | 94.39 | 60.55 | 35.91 | 14.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
409 | 12 | 2026-06-27 | 274 | 255.55 | 217.36 | 200.96 | 164.92 | 125.14 | 94.4 | 80.8 | 61.53 | 37.88 | 21.97 | 4.48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
410 | 8 | 2026-05-02 | 272 | 238.82 | 198.7 | 159.7 | 135.52 | 99.52 | 67.36 | 25.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
411 | 14 | 2026-07-25 | 342 | 322.4 | 290.01 | 252.84 | 232.44 | 202.28 | 177.32 | 160.94 | 132.74 | 102.49 | 85.72 | 63.94 | 33.52 | 7.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
412 | 16 | 2026-08-22 | 381 | 357.32 | 333.8 | 309.75 | 278.94 | 260.49 | 220.34 | 202.94 | 170.28 | 145.08 | 130.82 | 103.1 | 76.6 | 53.88 | 37.89 | 16.44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
413 | 10 | 2026-05-30 | 241 | 208.87 | 193.67 | 173.19 | 155.83 | 127.93 | 108.19 | 82.75 | 44.11 | 10.53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
414 | 12 | 2026-06-27 | 294 | 267.5 | 242.7 | 216.3 | 189.27 | 167.81 | 148.45 | 118.29 | 92.29 | 69.5 | 55.9 | 16.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
415 | 15 | 2026-08-08 | 382 | 341.2 | 315.16 | 296.05 | 268 | 248.68 | 217.08 | 193.83 | 170.43 | 134.52 | 111.58 | 91.45 | 64.99 | 38.53 | 8.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
416 | 9 | 2026-05-16 | 257 | 224.24 | 210.3 | 188.7 | 167.2 | 124.72 | 101.16 | 68.67 | 36.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
417 | 14 | 2026-07-25 | 347 | 317.96 | 292.04 | 270.2 | 250.2 | 227.41 | 201.17 | 177.23 | 146.15 | 114.33 | 93.21 | 66.41 | 29.75 | 1.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
418 | 13 | 2026-07-11 | 283 | 269.14 | 240.28 | 219.28 | 203.18 | 177.88 | 148.24 | 126.16 | 106.4 | 80.18 | 52.46 | 25.51 | 0.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
419 | 9 | 2026-05-16 | 296 | 249.6 | 231.97 | 187.73 | 157.73 | 132.29 | 87.89 | 47.18 | 21.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
420 | 19 | 2026-10-03 | 446 | 425.21 | 404.13 | 382.37 | 351.97 | 321.44 | 298.22 | 277.76 | 241.26 | 220.26 | 175.6 | 155.54 | 137.41 | 115.99 | 94.26 | 64.59 | 51.99 | 28.23 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
421 | 8 | 2026-05-02 | 212 | 185.54 | 149.14 | 111.14 | 86.94 | 55.26 | 38.06 | 14.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
422 | 13 | 2026-07-11 | 328 | 290.83 | 266.08 | 219.47 | 186.1 | 164.05 | 141.5 | 127.86 | 107.22 | 80.82 | 60.61 | 28.61 | 4.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
423 | 11 | 2026-06-13 | 278 | 252.92 | 210.92 | 184.46 | 147.89 | 127.74 | 100.02 | 85.22 | 65.13 | 43.2 | 22.9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
424 | 11 | 2026-06-13 | 267 | 229.2 | 204.82 | 185.21 | 163.82 | 146.72 | 128.24 | 98 | 77.84 | 44.24 | 19.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
425 | 12 | 2026-06-27 | 316 | 301.43 | 266.63 | 234.71 | 204.68 | 176.12 | 146.54 | 127.22 | 98.78 | 71.05 | 43.51 | 5.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
426 | 11 | 2026-06-13 | 344 | 309.96 | 292.46 | 252.86 | 225.13 | 187.69 | 145.03 | 106.63 | 87.76 | 56.96 | 16.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
427 | 13 | 2026-07-11 | 338 | 312.35 | 274.35 | 247.83 | 221.65 | 198.43 | 181.71 | 155.81 | 118.68 | 91.32 | 71.97 | 27.51 | 4.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
428 | 11 | 2026-06-13 | 346 | 328.4 | 294.96 | 253.16 | 230.61 | 194.13 | 161.13 | 125.29 | 90.29 | 46.21 | 32.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
429 | 10 | 2026-05-30 | 285 | 260.49 | 220.59 | 189.39 | 161.3 | 132.68 | 100.23 | 73.73 | 44.21 | 17.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
430 | 12 | 2026-06-27 | 363 | 336.35 | 290.53 | 260.5 | 228.58 | 193.18 | 150.78 | 122.88 | 104.4 | 66.66 | 38.34 | 20.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
431 | 10 | 2026-05-30 | 281 | 251 | 227.2 | 193.65 | 166.59 | 133.59 | 111.89 | 94.69 | 67.09 | 31.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
432 | 8 | 2026-05-02 | 238 | 202.04 | 176.08 | 145.92 | 107.97 | 79.47 | 46.71 | 12.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
433 | 13 | 2026-07-11 | 348 | 328.53 | 309.45 | 294.25 | 266.41 | 235.39 | 197.04 | 166.29 | 144.2 | 106.04 | 78.44 | 45.54 | 17.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
434 | 10 | 2026-05-30 | 287 | 248.84 | 211.1 | 174.14 | 148.76 | 115.65 | 88.05 | 73.79 | 33.75 | 9.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
435 | 13 | 2026-07-11 | 273 | 248.5 | 225.14 | 197.54 | 174.44 | 161.32 | 133.72 | 108.97 | 89.17 | 59.49 | 42.66 | 23.28 | 6.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
436 | 11 | 2026-06-13 | 246 | 225.42 | 188.16 | 161.94 | 127.78 | 103.3 | 81.8 | 63.76 | 48.64 | 25.24 | 11.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
437 | 13 | 2026-07-11 | 343 | 311.5 | 286.54 | 264.64 | 236.71 | 201.99 | 181.99 | 150.71 | 125.91 | 106.8 | 67.47 | 37.71 | 14.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
438 | 15 | 2026-08-08 | 428 | 399.14 | 379.46 | 358.55 | 323.35 | 291.01 | 251.59 | 216.8 | 176.65 | 150.52 | 131.41 | 108.47 | 82.85 | 60.05 | 20.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
439 | 12 | 2026-06-27 | 320 | 294.99 | 268.47 | 232.77 | 211.21 | 171.71 | 139.76 | 109.16 | 88.95 | 71.93 | 50.86 | 19.51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
440 | 13 | 2026-07-11 | 356 | 334.27 | 311.32 | 274.98 | 235.48 | 215.27 | 191.47 | 167.03 | 138.56 | 108.67 | 72.07 | 50.51 | 21.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
441 | 12 | 2026-06-27 | 294 | 271.2 | 247.75 | 222.79 | 194.67 | 161.61 | 143.13 | 116.25 | 99.85 | 76 | 43.24 | 25.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
442 | 10 | 2026-05-30 | 296 | 273.37 | 236.57 | 212.65 | 166.25 | 145.45 | 123.45 | 97.6 | 59.84 | 22.88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
443 | 15 | 2026-08-08 | 347 | 316.79 | 292.3 | 265.9 | 243.64 | 215.69 | 197.29 | 175.2 | 147.75 | 128.88 | 104.88 | 90.53 | 74.78 | 37.02 | 3.42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
444 | 16 | 2026-08-22 | 354 | 330.75 | 302.91 | 283.38 | 246.72 | 221.78 | 200.78 | 174.65 | 157.01 | 129.28 | 111.26 | 89.5 | 74.8 | 43.44 | 22.54 | 7.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
445 | 12 | 2026-06-27 | 323 | 303.73 | 274.5 | 240.33 | 203.67 | 179.29 | 146.29 | 129.79 | 111.79 | 75.58 | 49.06 | 18.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
446 | 13 | 2026-07-11 | 343 | 316.99 | 279.79 | 254.29 | 216.49 | 191.64 | 164.69 | 144.11 | 121.31 | 89.45 | 71.39 | 47.27 | 34.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
447 | 14 | 2026-07-25 | 370 | 338.64 | 303.83 | 262.22 | 239.12 | 208.4 | 188.4 | 165.6 | 152.1 | 124.15 | 100.23 | 72.15 | 39.82 | 1.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
448 | 17 | 2026-09-05 | 408 | 388.64 | 362.18 | 329.18 | 307.18 | 284.5 | 268.66 | 244.66 | 209.62 | 181.02 | 160.5 | 124.95 | 109.27 | 88.59 | 57.99 | 24.95 | 2.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
449 | 15 | 2026-08-08 | 381 | 348.55 | 318.62 | 295.22 | 273.32 | 241.64 | 221.4 | 200.01 | 178.01 | 159.13 | 116.65 | 87.77 | 72.6 | 32.28 | 2.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
450 | 10 | 2026-05-30 | 325 | 295.42 | 282.71 | 251.97 | 208.47 | 171.21 | 134.25 | 94.98 | 58.98 | 22.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
451 | 13 | 2026-07-11 | 352 | 327.85 | 299.29 | 260.94 | 232.27 | 208.07 | 179.55 | 151.06 | 115.96 | 86.07 | 65.57 | 30.92 | 7.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
452 | 10 | 2026-05-30 | 259 | 225.19 | 202.01 | 159.35 | 127.15 | 103.15 | 73.71 | 44.13 | 25.02 | 6.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
453 | 10 | 2026-05-30 | 260 | 225.96 | 200.12 | 167.87 | 134.83 | 94.79 | 73.35 | 54.44 | 27.78 | 6.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
454 | 12 | 2026-06-27 | 303 | 282.84 | 258.54 | 223.73 | 205.25 | 185.73 | 156.93 | 142.98 | 112.73 | 81.23 | 62.19 | 18.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
455 | 12 | 2026-06-27 | 309 | 276.36 | 249 | 227.3 | 185.86 | 163.18 | 139.42 | 125.98 | 102.88 | 65.75 | 36.6 | 20.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
456 | 12 | 2026-06-27 | 339 | 314.01 | 269.01 | 249.49 | 230.29 | 207.17 | 174.78 | 145.2 | 102.72 | 77.16 | 43.61 | 25.98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
457 | 10 | 2026-05-30 | 245 | 223.22 | 192.98 | 172.34 | 149.22 | 116.04 | 78.28 | 62.08 | 43.68 | 22.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
458 | 14 | 2026-07-25 | 357 | 341.5 | 298.43 | 273.23 | 232.73 | 209.69 | 184.89 | 161.37 | 138.97 | 120.37 | 97.8 | 67.9 | 46.82 | 22.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
459 | 14 | 2026-07-25 | 362 | 344.9 | 327.4 | 305.4 | 278.9 | 251.76 | 218.65 | 190.65 | 165.85 | 131.05 | 107.05 | 85.05 | 39.62 | 24.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
460 | 14 | 2026-07-25 | 381 | 358.77 | 333.35 | 305.75 | 267.25 | 243.85 | 221.59 | 192.34 | 149.27 | 116.84 | 93.89 | 69.39 | 45.61 | 7.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
461 | 14 | 2026-07-25 | 330 | 295.6 | 273.76 | 242.16 | 228.21 | 190.13 | 171.26 | 152.01 | 127.26 | 111.26 | 67.94 | 49.02 | 20.22 | 2.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
462 | 14 | 2026-07-25 | 376 | 333.25 | 317.08 | 289.72 | 256.12 | 216.12 | 193.08 | 153.18 | 122.52 | 91.8 | 74.52 | 51.16 | 33.16 | 10.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
463 | 10 | 2026-05-30 | 233 | 211.88 | 186.5 | 161.71 | 138.21 | 107.61 | 81.77 | 58.67 | 35.27 | 11.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
464 | 8 | 2026-05-02 | 218 | 200.8 | 164.23 | 135.35 | 102.05 | 70.13 | 31.73 | 12.93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
465 | 14 | 2026-07-25 | 328 | 311.8 | 293.6 | 271.6 | 249.1 | 229.32 | 208.44 | 188.49 | 148.73 | 124.25 | 86.52 | 58.52 | 26.09 | 2.41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
466 | 9 | 2026-05-16 | 251 | 214.79 | 191.42 | 176.3 | 135.12 | 113.04 | 85.68 | 46.63 | 20.45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
467 | 11 | 2026-06-13 | 315 | 279.49 | 247.49 | 205.37 | 172.31 | 145.43 | 120.47 | 94.97 | 70.33 | 37.69 | 18.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
468 | 11 | 2026-06-13 | 319 | 303.88 | 274.84 | 250.09 | 211.04 | 180.89 | 147.99 | 111.99 | 81.78 | 36.78 | 0.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
469 | 8 | 2026-05-02 | 256 | 238.66 | 208.66 | 165.74 | 130.64 | 98.3 | 58.02 | 24.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
470 | 10 | 2026-05-30 | 252 | 221.97 | 197.89 | 159.97 | 142.33 | 117.63 | 88.59 | 66.36 | 33.8 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
471 | 10 | 2026-05-30 | 289 | 248.85 | 220.35 | 178.35 | 145.85 | 111.65 | 88.55 | 60.47 | 26.84 | 7.08 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
472 | 14 | 2026-07-25 | 337 | 320.2 | 293.92 | 276.37 | 248.9 | 222.98 | 201.08 | 182.93 | 153.53 | 118.19 | 87.17 | 62.53 | 36.73 | 2.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
473 | 10 | 2026-05-30 | 254 | 212.56 | 197.6 | 172.18 | 148.26 | 122.02 | 98.37 | 72.27 | 39.94 | 0.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
474 | 11 | 2026-06-13 | 272 | 244.05 | 228.65 | 210.67 | 190.89 | 159.62 | 145.68 | 105.9 | 80.82 | 67.38 | 31.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
475 | 11 | 2026-06-13 | 319 | 289.93 | 266.81 | 230.9 | 203.7 | 174.55 | 160.75 | 138.43 | 109.43 | 74.63 | 41.87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
476 | 13 | 2026-07-11 | 328 | 294.16 | 280.66 | 249.31 | 231.29 | 202.87 | 175.92 | 137.73 | 115.62 | 99.28 | 71.2 | 39.07 | 3.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
477 | 13 | 2026-07-11 | 323 | 292.28 | 274.15 | 248.95 | 221.51 | 191.15 | 166.83 | 146.43 | 130.45 | 106.45 | 84.37 | 63.85 | 39.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
478 | 11 | 2026-06-13 | 266 | 251.38 | 234.46 | 218.95 | 203.91 | 171.96 | 145.64 | 107.16 | 71.8 | 26.8 | 11.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
479 | 13 | 2026-07-11 | 372 | 353.14 | 314.86 | 290.42 | 278.02 | 255.24 | 208.84 | 174.76 | 145.52 | 113.12 | 87.92 | 60.62 | 19.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
480 | 11 | 2026-06-13 | 327 | 308.2 | 262.6 | 239.5 | 211.62 | 170.44 | 144.17 | 107.59 | 80.23 | 60.02 | 24.62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
481 | 16 | 2026-08-22 | 390 | 368 | 346.17 | 323.6 | 299.8 | 276.12 | 239.55 | 211.17 | 184.89 | 169.53 | 134.88 | 113.04 | 93.84 | 78.54 | 39.21 | 19.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
482 | 11 | 2026-06-13 | 347 | 311 | 281.36 | 244.51 | 218.75 | 183.35 | 156.29 | 118.66 | 98.2 | 53.2 | 32.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
483 | 12 | 2026-06-27 | 291 | 266.52 | 242.43 | 226.79 | 186.5 | 143.6 | 124.38 | 104.78 | 67.16 | 50.99 | 26.15 | 2.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
484 | 13 | 2026-07-11 | 350 | 319.2 | 296.45 | 264.77 | 220.69 | 198.64 | 168.24 | 151.41 | 119.73 | 84.37 | 55.85 | 24.69 | 5.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
485 | 14 | 2026-07-25 | 319 | 297.4 | 283.96 | 245.32 | 213.96 | 190.93 | 169.43 | 148.28 | 132.08 | 115.68 | 80.58 | 65.73 | 47.28 | 16.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
486 | 12 | 2026-06-27 | 308 | 283.3 | 260.94 | 229.58 | 197.66 | 160.22 | 141.98 | 117.47 | 92.67 | 76.55 | 45.27 | 14.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
487 | 15 | 2026-08-08 | 398 | 370.55 | 339.2 | 316.17 | 284.25 | 264.51 | 243.36 | 212.56 | 187.36 | 158.11 | 134.79 | 94.08 | 59.78 | 30.98 | 1.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
488 | 12 | 2026-06-27 | 337 | 309.86 | 293.46 | 264.99 | 247.83 | 224.51 | 196.97 | 164.48 | 138.56 | 92.96 | 61.47 | 21.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
489 | 10 | 2026-05-30 | 245 | 218.21 | 200.15 | 184.85 | 147.33 | 118.83 | 97.51 | 67.87 | 47.22 | 27.38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
490 | 11 | 2026-06-13 | 247 | 215 | 183.5 | 151.1 | 128.09 | 102.13 | 82.33 | 70.03 | 52.35 | 35.55 | 13.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
491 | 9 | 2026-05-16 | 236 | 200.81 | 172.31 | 139.19 | 114.69 | 83.12 | 64.32 | 37.26 | 9.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
492 | 13 | 2026-07-11 | 339 | 314.91 | 291.69 | 268.17 | 241.08 | 205.2 | 177.15 | 152.4 | 122.51 | 101.19 | 80.51 | 56.15 | 19.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
493 | 16 | 2026-08-22 | 416 | 394.7 | 370.28 | 342.72 | 300.72 | 269.1 | 233.7 | 209.85 | 190.71 | 158.26 | 129.45 | 102.44 | 69 | 48.75 | 19.47 | 5.97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
494 | 12 | 2026-06-27 | 309 | 284.3 | 257.9 | 239.18 | 205.9 | 183.58 | 153.66 | 133.18 | 94.54 | 69.58 | 44.17 | 12.27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
495 | 14 | 2026-07-25 | 364 | 342.27 | 316.53 | 291.33 | 259.21 | 219.01 | 178.54 | 160.6 | 131.1 | 101.46 | 77.02 | 60.92 | 41.31 | 15.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
496 | 11 | 2026-06-13 | 325 | 292.87 | 269.93 | 234.02 | 214.18 | 177.08 | 156.08 | 123.28 | 83.24 | 41.64 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
497 | 11 | 2026-06-13 | 310 | 281.14 | 256.94 | 223.88 | 205.88 | 175.64 | 156.37 | 131.46 | 93.11 | 59.27 | 26.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
498 | 10 | 2026-05-30 | 253 | 235.33 | 207.59 | 180.33 | 148.13 | 119.63 | 79.34 | 55.04 | 30.03 | 6.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
499 | 12 | 2026-06-27 | 366 | 328.88 | 283.28 | 255.28 | 232.18 | 206.22 | 162.9 | 123.9 | 101.1 | 67.52 | 22.09 | 5.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
500 | 10 | 2026-05-30 | 282 | 258.99 | 226.16 | 205.76 | 167.36 | 140.08 | 122.16 | 83.28 | 53.76 | 24.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
501 | 10 | 2026-05-30 | 299 | 274.82 | 255.47 | 236.36 | 194.02 | 159.25 | 128.47 | 90.13 | 50.53 | 15.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
502 | 16 | 2026-08-22 | 375 | 348.77 | 330.85 | 316.15 | 291.07 | 263.47 | 242.32 | 226.12 | 207.04 | 190.04 | 149.44 | 123.22 | 95.78 | 73.7 | 46.26 | 20.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
503 | 12 | 2026-06-27 | 299 | 269.85 | 256.25 | 227.9 | 198 | 173.56 | 149.05 | 121.49 | 96.89 | 80.98 | 56.66 | 26.11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
504 | 10 | 2026-05-30 | 274 | 255.96 | 222.36 | 195.27 | 178.47 | 143.7 | 108.34 | 74.54 | 48.5 | 28.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
505 | 15 | 2026-08-08 | 366 | 342.22 | 296.62 | 271.09 | 245.17 | 215.17 | 188.03 | 174.7 | 155.48 | 125.08 | 99.16 | 66.16 | 48.53 | 25.57 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
506 | 14 | 2026-07-25 | 389 | 369.76 | 342.2 | 302.3 | 261.98 | 242.09 | 218.31 | 194.55 | 150.55 | 117.27 | 94.87 | 70.82 | 53.22 | 11.82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
507 | 11 | 2026-06-13 | 267 | 229.04 | 206.99 | 178.19 | 159.49 | 130.97 | 114.17 | 89.57 | 59.57 | 32.12 | 4.39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
508 | 11 | 2026-06-13 | 256 | 229.36 | 210.11 | 184.63 | 155.39 | 130.43 | 107.8 | 90.31 | 60.7 | 33.26 | 6.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
509 | 14 | 2026-07-25 | 321 | 297.03 | 275.02 | 243.82 | 225.42 | 202.63 | 172.54 | 142.51 | 118.59 | 95.19 | 76.39 | 41.61 | 25.51 | 3.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
510 | 10 | 2026-05-30 | 216 | 200.36 | 173.84 | 151.4 | 112.2 | 91.3 | 68.5 | 50.1 | 35.7 | 4.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
511 | 13 | 2026-07-11 | 303 | 282.6 | 247.95 | 217.61 | 174.69 | 156.45 | 134.25 | 101.69 | 79.49 | 62.99 | 35.69 | 18.53 | 0.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
512 | 12 | 2026-06-27 | 298 | 276.4 | 252.31 | 223.51 | 200.73 | 162.81 | 131.07 | 105.69 | 80.94 | 57.74 | 31.82 | 4.28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
513 | 12 | 2026-06-27 | 332 | 313.1 | 268.07 | 253.11 | 212.07 | 190.07 | 173.97 | 135.11 | 103.61 | 88.49 | 42.29 | 11.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
514 | 13 | 2026-07-11 | 347 | 314.6 | 297.88 | 270.52 | 225.49 | 204.61 | 176.55 | 142.8 | 110.88 | 82.72 | 45.67 | 24.05 | 10.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
515 | 12 | 2026-06-27 | 354 | 330.03 | 295.24 | 258.84 | 220.89 | 197.11 | 174.55 | 146.62 | 118.88 | 72.27 | 33.51 | 1.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
516 | 16 | 2026-08-22 | 364 | 342.58 | 321.86 | 302.5 | 282.41 | 265.01 | 245.54 | 213.62 | 183.28 | 148.08 | 131.42 | 116.02 | 95.22 | 63.32 | 48.28 | 24.78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
517 | 10 | 2026-05-30 | 270 | 250.24 | 210.82 | 193.22 | 171.17 | 148.37 | 110.57 | 73.13 | 37.73 | 13.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
518 | 13 | 2026-07-11 | 376 | 352.5 | 308.26 | 274.34 | 249.4 | 218.6 | 197 | 160.52 | 135.06 | 105.54 | 74.34 | 52.29 | 26.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
519 | 15 | 2026-08-08 | 355 | 341.47 | 313.33 | 300.73 | 282.87 | 254.49 | 218.79 | 198.7 | 174.06 | 145.94 | 126.74 | 100.34 | 75.92 | 44.43 | 29.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
520 | 14 | 2026-07-25 | 339 | 315 | 297.15 | 282.75 | 253.75 | 231.25 | 218.35 | 174.85 | 151.05 | 119.55 | 82.42 | 56.02 | 40.04 | 11.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
521 | 11 | 2026-06-13 | 288 | 256.32 | 235.97 | 209.79 | 175.49 | 148.19 | 124.79 | 96.29 | 74.24 | 47.59 | 22.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
522 | 16 | 2026-08-22 | 403 | 378.91 | 349.77 | 327.69 | 315.29 | 286.82 | 256.61 | 229.01 | 198.65 | 174.89 | 141.99 | 125.27 | 105.21 | 74.61 | 53.61 | 9.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
523 | 10 | 2026-05-30 | 262 | 230.28 | 210.33 | 186.73 | 164.53 | 132.58 | 108.78 | 73.94 | 47.54 | 18.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
524 | 13 | 2026-07-11 | 296 | 273.06 | 254.77 | 237.67 | 211.84 | 187.79 | 162.95 | 135.59 | 117.67 | 87.58 | 70.81 | 32.31 | 12.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
525 | 15 | 2026-08-08 | 372 | 340.14 | 307.74 | 295.44 | 275.7 | 251.7 | 227.58 | 198.14 | 171.89 | 135.29 | 114.22 | 92.22 | 66.09 | 45.94 | 23.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
526 | 11 | 2026-06-13 | 264 | 232.04 | 208.94 | 183.34 | 161.34 | 134.94 | 112.84 | 86.04 | 54.72 | 34.42 | 13.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
527 | 16 | 2026-08-22 | 372 | 358.67 | 324.86 | 299.26 | 279.2 | 253.2 | 223.17 | 203.82 | 187.92 | 152.92 | 123.77 | 85.13 | 65.13 | 42.93 | 24.45 | 0.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
528 | 12 | 2026-06-27 | 327 | 298.48 | 274.4 | 241.92 | 212.72 | 183.22 | 143.22 | 118.02 | 90.74 | 67.28 | 36.68 | 15.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
529 | 14 | 2026-07-25 | 355 | 338.68 | 298.56 | 263.01 | 242.95 | 224.07 | 196.62 | 175.85 | 145.07 | 111.03 | 86.95 | 65.67 | 37.11 | 4.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
530 | 13 | 2026-07-11 | 339 | 321.72 | 305.27 | 275.69 | 239.69 | 220.09 | 204.51 | 159.51 | 126.57 | 101.61 | 76.17 | 57.84 | 26.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
531 | 11 | 2026-06-13 | 306 | 282.82 | 236.02 | 209.47 | 174.28 | 156.43 | 120.22 | 103 | 63.78 | 24.25 | 4.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
532 | 11 | 2026-06-13 | 295 | 258.04 | 221.83 | 198.79 | 172.83 | 137.33 | 96.53 | 70.56 | 48.01 | 34.21 | 16.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
533 | 12 | 2026-06-27 | 300 | 262.38 | 242.03 | 211.82 | 184.68 | 158.16 | 139.36 | 125.83 | 77.83 | 52.63 | 31.03 | 12.79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
534 | 12 | 2026-06-27 | 293 | 277.16 | 239.56 | 214.72 | 190.78 | 168.34 | 141.46 | 115.46 | 80.9 | 45.13 | 18.58 | 2.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
535 | 8 | 2026-05-02 | 237 | 198.5 | 170.15 | 132.45 | 103.2 | 65.97 | 35.63 | 6.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
536 | 11 | 2026-06-13 | 294 | 258.48 | 226.23 | 195.03 | 154.91 | 128.94 | 110.94 | 87 | 65.76 | 50.8 | 19.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
537 | 13 | 2026-07-11 | 386 | 357.02 | 315.98 | 289.03 | 267.43 | 227.68 | 192.17 | 158.57 | 138.97 | 115.93 | 82.78 | 60.28 | 30.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
538 | 13 | 2026-07-11 | 301 | 268.32 | 245.44 | 233.14 | 205.88 | 190.84 | 167.96 | 149.1 | 133.12 | 98.92 | 80.59 | 51.97 | 23.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
539 | 9 | 2026-05-16 | 298 | 274.06 | 229.82 | 192.77 | 160.57 | 137.39 | 104.99 | 67.73 | 35.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
540 | 9 | 2026-05-16 | 211 | 190 | 154.58 | 131.26 | 96.46 | 75.94 | 40.58 | 24.62 | 2.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
541 | 13 | 2026-07-11 | 358 | 330.64 | 308.56 | 271.36 | 252.88 | 217.37 | 188.81 | 168.31 | 137.15 | 118.07 | 76.82 | 51.06 | 17.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
542 | 9 | 2026-05-16 | 239 | 221.45 | 199.09 | 161.49 | 134.65 | 111.25 | 88.69 | 50.93 | 13.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
543 | 13 | 2026-07-11 | 338 | 295.6 | 260.32 | 234.32 | 220.72 | 193.69 | 157.12 | 134.89 | 121.13 | 90.77 | 65.36 | 40.35 | 13.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
544 | 12 | 2026-06-27 | 321 | 281.4 | 245.98 | 215.96 | 180.76 | 159.85 | 125.63 | 107.65 | 86.03 | 50.33 | 30.72 | 9.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
545 | 10 | 2026-05-30 | 264 | 228.81 | 201.81 | 178.69 | 137.44 | 123.91 | 95.91 | 57.56 | 31.34 | 1.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
546 | 15 | 2026-08-08 | 388 | 353.04 | 324.6 | 289.32 | 270.28 | 235.88 | 211.08 | 168.73 | 142.18 | 121.48 | 105.48 | 81.63 | 67.23 | 33.59 | 13.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
547 | 12 | 2026-06-27 | 318 | 282.96 | 268.2 | 240.36 | 201.16 | 166.06 | 148.08 | 118.68 | 85.04 | 55.89 | 36.51 | 22.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
548 | 14 | 2026-07-25 | 320 | 302.78 | 286.28 | 266.93 | 248.02 | 224.62 | 202.51 | 178.64 | 147.37 | 120.07 | 96.85 | 78.85 | 40.5 | 5.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
549 | 10 | 2026-05-30 | 249 | 218.84 | 184.03 | 157.57 | 132.82 | 105.87 | 82.92 | 63.12 | 44.22 | 29.94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
550 | 18 | 2026-09-19 | 426 | 404 | 374.42 | 341.36 | 322.55 | 306.23 | 283.19 | 253.19 | 230.18 | 215.61 | 187.41 | 169.81 | 143.21 | 109.17 | 82.94 | 54.52 | 36.58 | 9.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
551 | 8 | 2026-05-02 | 225 | 194.32 | 163.64 | 149.29 | 116.35 | 84.01 | 55.21 | 13.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
552 | 10 | 2026-05-30 | 285 | 262.68 | 229.2 | 191.68 | 169.14 | 146.2 | 118.2 | 94.8 | 63.18 | 32.58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
553 | 10 | 2026-05-30 | 230 | 217.4 | 198.15 | 170.55 | 153.89 | 134.69 | 111.66 | 90.31 | 51.37 | 11.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
554 | 11 | 2026-06-13 | 343 | 303 | 282.84 | 255.84 | 215.8 | 196 | 156.25 | 110.82 | 69.94 | 30.41 | 15.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
555 | 13 | 2026-07-11 | 353 | 317.72 | 287.34 | 254.89 | 226.75 | 208.71 | 174.39 | 152.61 | 115.86 | 83.01 | 63.21 | 49.26 | 23.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
556 | 10 | 2026-05-30 | 238 | 214.9 | 188.58 | 158.22 | 138.87 | 113.67 | 87.39 | 52.94 | 23.24 | 3.64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
557 | 15 | 2026-08-08 | 377 | 357.2 | 322.64 | 299.96 | 273.86 | 238.46 | 212.06 | 172.06 | 144.7 | 122.62 | 98.32 | 77.92 | 53.78 | 25.08 | 4.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
558 | 14 | 2026-07-25 | 343 | 323.64 | 305.14 | 287.8 | 270.8 | 229.22 | 211.37 | 182.7 | 162.03 | 144.93 | 115.78 | 86.1 | 54.5 | 19.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
559 | 12 | 2026-06-27 | 323 | 301.4 | 264.9 | 223.65 | 200.22 | 174.38 | 153.26 | 123.76 | 91.28 | 70.58 | 46.98 | 16.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
560 | 15 | 2026-08-08 | 377 | 335.7 | 319.05 | 287.81 | 263.62 | 232.38 | 214.75 | 179.5 | 153.04 | 124.06 | 92.7 | 76.95 | 51.99 | 28.67 | 6.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
561 | 11 | 2026-06-13 | 280 | 261 | 227.56 | 208.84 | 184.06 | 161.1 | 124.62 | 112.22 | 81.72 | 57.21 | 24.21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
562 | 11 | 2026-06-13 | 287 | 264.44 | 238.79 | 210.12 | 178.84 | 155.84 | 132.88 | 104.79 | 72.97 | 43.53 | 2.72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
563 | 9 | 2026-05-16 | 235 | 196.12 | 178.45 | 150.91 | 133.69 | 87.87 | 68.15 | 51.87 | 19.47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
564 | 12 | 2026-06-27 | 291 | 272.76 | 242.34 | 228.58 | 211.92 | 190.14 | 170.42 | 156.07 | 118.81 | 85.91 | 49.61 | 26.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
565 | 12 | 2026-06-27 | 269 | 245.21 | 217.09 | 196.88 | 174.62 | 151.19 | 128.63 | 106.19 | 82.74 | 68.79 | 41.04 | 24.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
566 | 12 | 2026-06-27 | 302 | 273.44 | 250.94 | 230.64 | 207.04 | 174.65 | 159.95 | 135.77 | 106.29 | 65.82 | 40.86 | 10.04 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
567 | 14 | 2026-07-25 | 366 | 337.2 | 316.74 | 296.65 | 278.41 | 259.55 | 241.15 | 202.15 | 163.81 | 139.69 | 103.85 | 73.05 | 38.25 | 8.77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
568 | 12 | 2026-06-27 | 301 | 273.27 | 247.03 | 218.43 | 194.51 | 175.71 | 153.87 | 131.82 | 88.75 | 62.57 | 32.15 | 9.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
569 | 10 | 2026-05-30 | 284 | 243.96 | 215.9 | 185.81 | 153.32 | 125.32 | 87.88 | 63.24 | 39.46 | 13.06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
570 | 15 | 2026-08-08 | 373 | 342.4 | 315.94 | 294.49 | 252.6 | 229.8 | 213 | 195.4 | 161.32 | 142.32 | 120.12 | 76.67 | 41.86 | 26.02 | 4.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
571 | 13 | 2026-07-11 | 346 | 332.05 | 302.35 | 264.39 | 233.19 | 205.31 | 176.79 | 134.99 | 117.31 | 74.11 | 55.51 | 39.31 | 14.23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
572 | 12 | 2026-06-27 | 320 | 285.5 | 252.32 | 235.55 | 209.63 | 186.63 | 151.84 | 129.44 | 97.72 | 67.04 | 33.5 | 15.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
573 | 15 | 2026-08-08 | 380 | 360.64 | 329.44 | 294.67 | 266.27 | 247.94 | 232.26 | 207.76 | 172.01 | 147.26 | 122.96 | 94.36 | 58.64 | 40.79 | 8.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
574 | 11 | 2026-06-13 | 273 | 249.3 | 227.68 | 207.55 | 173.63 | 154.03 | 132.43 | 87.59 | 68.21 | 31.11 | 9.18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
575 | 9 | 2026-05-16 | 232 | 194.26 | 166.33 | 135.73 | 110.29 | 90.61 | 68.5 | 41.95 | 8.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
576 | 15 | 2026-08-08 | 338 | 309.3 | 292.15 | 270.07 | 249.61 | 220.75 | 201.22 | 184.41 | 165.96 | 125.25 | 110.53 | 87.73 | 73.01 | 54.81 | 20.59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
577 | 13 | 2026-07-11 | 370 | 348.54 | 324.6 | 302.7 | 273.47 | 246.02 | 210.92 | 172.57 | 140.07 | 103.59 | 73.23 | 38.73 | 17.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
578 | 15 | 2026-08-08 | 400 | 367.88 | 339.68 | 311.33 | 292.29 | 265.29 | 240.81 | 221.61 | 198.57 | 169.37 | 132.17 | 114.69 | 84.69 | 45.49 | 1.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
579 | 12 | 2026-06-27 | 315 | 291.24 | 265.32 | 249.81 | 219.65 | 193.01 | 170.59 | 131.26 | 91.3 | 59.5 | 27.07 | 5.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
580 | 14 | 2026-07-25 | 384 | 348.01 | 330.38 | 299.58 | 263.04 | 240.72 | 217.84 | 190.24 | 162.59 | 136.07 | 102.19 | 83.74 | 48.54 | 30.91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
581 | 12 | 2026-06-27 | 346 | 319.48 | 284.23 | 262.67 | 230.33 | 207.39 | 172.62 | 138.62 | 107.75 | 73.83 | 37.23 | 3.31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
582 | 11 | 2026-06-13 | 301 | 270.4 | 242.11 | 219.71 | 194.16 | 171.28 | 125.46 | 84.42 | 71.4 | 53.77 | 25.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
583 | 10 | 2026-05-30 | 264 | 242.27 | 221.12 | 195.92 | 163.96 | 148.32 | 106.45 | 83.05 | 45.25 | 30.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
584 | 12 | 2026-06-27 | 322 | 282.5 | 253.24 | 229.04 | 208.24 | 191.02 | 171.49 | 137.52 | 101.52 | 78.27 | 39.79 | 9.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
585 | 15 | 2026-08-08 | 342 | 316.44 | 296.66 | 270.14 | 245.74 | 217.9 | 199.96 | 181.48 | 156.2 | 129.56 | 108.49 | 81.97 | 51.17 | 28.37 | 1.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
586 | 9 | 2026-05-16 | 215 | 190.7 | 164.2 | 148.22 | 123.78 | 96.48 | 70.72 | 35.38 | 18.74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
587 | 13 | 2026-07-11 | 315 | 299.6 | 259.64 | 226.7 | 212.94 | 194.81 | 159.83 | 132.57 | 119.86 | 84.52 | 55.82 | 41.42 | 26.22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
588 | 10 | 2026-05-30 | 238 | 220.45 | 202.43 | 167.18 | 139.18 | 106.52 | 93.72 | 68.22 | 49.11 | 24.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
589 | 8 | 2026-05-02 | 216 | 180.72 | 155.16 | 128.64 | 85.98 | 67.17 | 42.79 | 25.03 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
590 | 9 | 2026-05-16 | 237 | 213.03 | 188.28 | 158.84 | 132.84 | 96.54 | 64.09 | 43.85 | 7.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
591 | 9 | 2026-05-16 | 216 | 176.78 | 153.66 | 132.36 | 118.56 | 96.72 | 61.92 | 42.78 | 18.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
592 | 12 | 2026-06-27 | 313 | 281.15 | 244.35 | 208.8 | 186.25 | 171.73 | 138.61 | 112.78 | 82.1 | 57.6 | 23.4 | 8.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
593 | 13 | 2026-07-11 | 323 | 310.29 | 291.09 | 252.75 | 231.63 | 198.26 | 173.9 | 129.24 | 106.92 | 86.76 | 59.29 | 43.45 | 5.65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
594 | 12 | 2026-06-27 | 278 | 261.5 | 246.45 | 222.25 | 205.2 | 180 | 151.4 | 128.46 | 101.48 | 70.68 | 39.41 | 20.69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
595 | 14 | 2026-07-25 | 372 | 353.5 | 322.72 | 289.6 | 260.46 | 232.86 | 195.9 | 171.96 | 153.83 | 126.08 | 108.8 | 82 | 59.96 | 24.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
596 | 14 | 2026-07-25 | 356 | 326.6 | 299.04 | 279.69 | 254.91 | 239.51 | 216.11 | 172.91 | 156.25 | 124.98 | 103.14 | 81.69 | 39.57 | 19.36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
597 | 12 | 2026-06-27 | 301 | 274.2 | 257.1 | 230.15 | 207.05 | 193.25 | 162.51 | 142.73 | 105.5 | 81.41 | 59.65 | 29.63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
598 | 12 | 2026-06-27 | 303 | 280.12 | 260.59 | 239.35 | 209.2 | 174.98 | 157.48 | 122.38 | 91.66 | 47.41 | 32.56 | 13.76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
End of Zero Week = IF([Weeks to Zero]<>"",INDEX(D2:BD2,1,[Weeks to Zero]+1),"")